## 00 Read Me
ISO/IEC 27001:2022 IMPLEMENTATION & ASSESSMENT WORKBOOK
ISO/IEC 27001:2022 Implementation Kit · sameerkhairkar.com ¦ Organisation: [YOUR ORGANISATION] ¦ Version 1.0 ¦ Date: [DATE]
WHAT THIS IS | A line-by-line implementation tool for ISO/IEC 27001:2022. Every requirement of Clauses 4-10 and all 93 Annex A controls appear as their own row, so nothing can be quietly skipped. It works as a gap assessment, a Statement of Applicability, a project tracker and an evidence index at the same time.
HOW TO USE IT | 1. Read '14 Implementation Plan' to understand the six milestones. 2. Work through '02 Clauses 4-10' and '03 Annex A and SoA' row by row. For each row set the status, the owner, a target date and where the evidence lives. 3. On the Annex A tab, the 'Applicable', 'Justification' and 'How it is implemented' columns together form your Statement of Applicability - a mandatory document. 4. Populate the risk tabs before finalising applicability decisions. Risk drives the SoA, not the other way round. 5. Watch '01 Dashboard' move. It is driven by formulas - do not overwrite it.
WHICH CELLS DO I FILL IN? | Any cell with a pale teal background is for you to complete. Cells on a GREY background are reference content - guidance, requirement text, milestone. Leave them alone. WHITE cells on the Dashboard are formulas. Overwriting them breaks the rollup. Rows in GREY ITALIC marked 'EXAMPLE' show the expected format. Delete or overwrite them once you start.
STATUS DEFINITIONS | Not Started - nothing in place. In Progress - being built, not yet operating. Implemented - in place and operating, evidence exists. Verified - independently checked (internal audit or independent review) and confirmed. Not Applicable - excluded, with a justification recorded. Only valid on the Annex A tab; Clause 4-10 requirements cannot be excluded.
MATURITY SCALE | 0 None - does not exist. 1 Initial - ad hoc, person-dependent. 2 Repeatable - done consistently but undocumented. 3 Defined - documented and followed. 4 Managed - measured and reported. 5 Optimising - continually improved.
THE SIX MILESTONES | M1 Mandate & Scope ¦ M2 Risk & Applicability ¦ M3 Core Documentation ¦ M4 Control Build-out ¦ M5 Operate & Evidence ¦ M6 Audit & Certify. Work milestones roughly in order. M4 and M5 overlap heavily. You cannot compress M5 - certification bodies want to see the ISMS having actually operated, typically for at least three months.
TABS AT A GLANCE | 01 Dashboard - live completion rollup. 02 Clauses 4-10 - the management system requirements. Non-negotiable, none can be excluded. 03 Annex A and SoA - all 93 controls plus the Statement of Applicability columns. 04 Mandatory Documents - the documents and records an auditor will ask for by name. 05 Document Register - every ISMS document and record, internal and external (7.5). 06 Interested Parties - Clause 4.2 register. 07 Asset Inventory - feeds risk assessment and A.5.9. 08 Risks and Opportunities - Clause 6.1.1. Risks to the MANAGEMENT SYSTEM. Not the same as tab 09. 09 Risk Register - Clause 6.1.2 and 8.2. Risks to your INFORMATION. 10 Risk Treatment Plan - Clause 6.1.3 and 8.3. 11 RACI - who does what across ISMS processes. 12 Competence Matrix - Clause 7.2, including the mandatory evidence of competence. 13 Communication Plan - Clause 7.4: on what, when, with whom, how. 14 Implementation Plan - milestones, phases and exit criteria. 15 Evidence Log - what you will hand the auditor, and where it lives. 16 Nonconformities - Clause 10.2 corrective action log. 17 Objectives - Clause 6.2. Objectives at relevant functions and levels. 18 Measurement Plan - Clause 9.1, specified using the ISO/IEC 27004 descriptors. 19 ISMS Change Log - Clause 6.3, planning of changes to the management system. 20 Exceptions Register - where every policy sends its exceptions. 21 Legal Register - A.5.31, A.5.32, A.5.34. 22 Supplier Register - A.5.19 to A.5.23, tiered by risk. 23 Retention Schedule - 7.5.3 and A.5.33: how long, and what happens after. 24 Cloud Responsibility - A.5.23 shared responsibility, one row per service. 25 Continual Improvement - Clause 10.1. Not the same as the nonconformity log. 26 Lookups - dropdown source lists. Editing these changes the dropdowns.
COMMON FAILURE POINTS | - An SoA that says 'Not applicable' with no justification. Auditors open this first. - Risk assessment written after the SoA, so the two do not agree. - No evidence the ISMS operated. Policies dated the week before the audit are obvious. - Internal audit performed by the person who built the ISMS. That is not independent. - Management review held as a five-minute item in another meeting, with no data pack. - Objectives that are not measurable, so Clause 9.1 has nothing to report on.
A NOTE ON SOURCES | Control reference numbers and short control titles are the identifiers used by ISO/IEC 27001:2022 Annex A. All requirement wording, guidance, evidence suggestions and commentary in this workbook are original text written for this kit and are not reproduced from ISO/IEC 27001 or ISO/IEC 27002, which are copyright ISO/IEC. Anyone implementing the standard should hold a licensed copy of ISO/IEC 27001:2022 and ISO/IEC 27002:2022.

## 01 Dashboard
ISMS IMPLEMENTATION DASHBOARD
All figures are formulas driven by the '02 Clauses 4-10' and '03 Annex A and SoA' tabs. Do not type over them.
CLAUSES 4-10 (management system requirements)
| Total | Not Started | In Progress | Implemented | Verified | % Complete
Count | 54 | 54 | 0 | 0 | 0 | 0%
ANNEX A CONTROLS (93) - custom controls are tracked on the tab but excluded from these counts
| Total | Applicable | Excluded | Not Started | In Progress | Implemented | Verified
Count | 93 | 93 | 0 | 92 | 0 | 1 | 0
% of applicable controls done | 1.075%
ANNEX A BY THEME (applicable controls only)
Theme | Applicable | Implemented or Verified | % Complete
Organizational | 37 | 1 | 2.703%
People | 8 | 0 | 0%
Physical | 14 | 0 | 0%
Technological | 34 | 0 | 0%
PROGRESS BY MILESTONE (clauses and controls combined)
Milestone | Items | Done | % Complete
M1 - Mandate & Scope | 16 | 0 | 0%
M2 - Risk & Applicability | 14 | 0 | 0%
M3 - Core Documentation | 15 | 1 | 6.667%
M4 - Control Build-out | 75 | 0 | 0%
M5 - Operate & Evidence | 14 | 0 | 0%
M6 - Audit & Certify | 13 | 0 | 0%
CERTIFICATION READINESS FLAGS
Check | Count | Target
Annex A rows still with no applicability decision | 0 | Must be 0 before the SoA is issued
Applicable controls with no inclusion justification | 92 | Must be 0 - auditors check every row
Excluded controls with no exclusion reason selected | 0 | Must be 0 - the commonest Stage 1 finding
Controls justified by risk assessment with no risk ID recorded | 0 | Should be 0 - ISO/IEC 27003 6.1.3 b) expects control-to-risk traceability
Implemented or Verified controls with no evidence reference | 0 | Should be 0 - claim without evidence fails at Stage 2
Clause requirements with no owner | 54 | Should be 0
Applicable controls with no owner | 92 | Should be 0
Objectives with any of the five Clause 6.2 planning elements blank | 0 | Should be 0 - 6.2 f) to j)
Effectiveness measures in the measurement plan | 7 | Should be 2 or more - Clause 9.1 wants effectiveness, not only performance

## 02 Clauses 4-10
CLAUSES 4-10 - MANAGEMENT SYSTEM REQUIREMENTS
Every row is a requirement. None of these can be excluded. Fill the tinted columns.
Ref | Clause | Requirement in plain English | What 'done' looks like | Typical evidence | Milestone | Mandatory documented information? | Status | Maturity | Owner | Target date | Evidence reference / location | Notes and gaps
4.1 | Understanding the organization and its context | Identify the external and internal issues that affect whether your ISMS can deliver the security outcomes you need. | A short, dated context analysis naming real issues (market, regulation, technology, staffing, culture, group structure) and why each one matters to security. Reviewed at least annually. | ISMS Context Analysis document; PESTLE/SWOT worksheet; management review minutes referencing context changes | M1 - Mandate & Scope | No (but expected) | Not Started | 0 - None
4.1 Amd | Climate change as a relevant issue (Amd 1:2024) | Determine whether climate change is a relevant issue for your organisation, and record the determination either way. | A short, reasoned statement in the context analysis. If it is relevant - data centre cooling and power, flood or heat risk to sites, supplier concentration in exposed regions, regulatory reporting obligations - the issues go into the context analysis and any resulting risk into the risk register like any other. If it is not relevant, say so and give the reason. | ISMS Context Analysis with an explicit climate change determination; risk register entries where relevant; management review minutes | M1 - Mandate & Scope | No (but the determination is expected) | Not Started | 0 - None
4.2 a-b | Needs and expectations of interested parties | List the parties with a stake in your information security and record what each one actually requires of you. | A register naming customers, regulators, employees, investors, suppliers, insurers, authorities - with the specific obligation each imposes (contract clause, law, certification, SLA). | Interested Parties Register; Legal & Contractual Requirements Register | M1 - Mandate & Scope | No (but expected) | Not Started | 0 - None
4.2 c | Requirements addressed through the ISMS | Decide which of those requirements the ISMS itself will satisfy, as opposed to being handled elsewhere in the business. | The register has a column marking in-scope vs. out-of-scope requirements, with a reason for each exclusion. | Interested Parties Register with 'addressed by ISMS' column completed | M1 - Mandate & Scope | No (but expected) | Not Started | 0 - None
4.2 Amd | Interested party requirements related to climate change (Amd 1:2024) | Consider whether any relevant interested party has requirements relating to climate change, and record what you found. | The interested parties register has been reviewed with climate change in mind - customer ESG questionnaires, investor or parent reporting, insurer expectations, regulatory disclosure regimes - and the answer is recorded, including where the answer is none. | Interested Parties Register with the climate change review dated; customer ESG questionnaire responses | M1 - Mandate & Scope | No (but the determination is expected) | Not Started | 0 - None
4.3 | Determining the scope of the ISMS | Define and document the boundaries of the ISMS, taking account of context, interested-party requirements, and the interfaces and dependencies with things you do not control. | A scope statement naming the products/services, locations, legal entities, business units, networks and systems included - plus explicit exclusions with justification, and how interfaces with excluded parties are managed. | ISMS Scope Document (approved and version-controlled); network/site diagram; org chart | M1 - Mandate & Scope | YES - mandatory | Not Started | 0 - None
4.4 | Information security management system | Actually establish, run, maintain and improve an ISMS, including the processes it needs and how those processes connect. | A process map or list of ISMS processes with named owners, inputs, outputs and interactions. Not just documents on a shelf. | ISMS Process Model / Framework document; RACI chart; process descriptions | M1 - Mandate & Scope | No (but expected) | Not Started | 0 - None
5.1 a | Leadership - policy and objectives | Top management must ensure the security policy and objectives are set and fit the organisation's strategic direction. | Policy and objectives signed off by top management and demonstrably linked to business strategy, not copy-pasted from a template. | Signed Information Security Policy; approved objectives; board/exco minutes | M1 - Mandate & Scope | No | Not Started | 0 - None
5.1 b | Leadership - integration into business processes | Top management must ensure ISMS requirements are built into the organisation's existing business processes. | Security steps visible inside HR onboarding, procurement, change management, project gates - not run as a separate parallel process. | Process documents showing embedded security steps; project gate checklists | M1 - Mandate & Scope | No | Not Started | 0 - None
5.1 c | Leadership - resources | Top management must make the resources the ISMS needs actually available. | Approved budget line, allocated headcount or contracted external support, tooling purchased. | Approved ISMS budget; resource plan; job descriptions; purchase orders | M1 - Mandate & Scope | No | Not Started | 0 - None
5.1 d-e | Leadership - communication and outcomes | Top management must communicate why effective security management matters and why conforming to the ISMS matters, and ensure the ISMS achieves its intended results. | Leadership-authored comms (all-hands, intranet post, email from CEO) plus evidence they track whether the ISMS is working. | All-hands slides; CEO/CISO communications; management review minutes | M1 - Mandate & Scope | No | Not Started | 0 - None
5.1 f-h | Leadership - direction, improvement, supporting other managers | Top management must direct and support people contributing to the ISMS, promote continual improvement, and back up other managers within their areas. | Visible sponsorship: attendance at the security committee, improvement actions personally owned, managers held to security objectives. | Security committee terms of reference and attendance records; objectives in manager performance plans | M1 - Mandate & Scope | No | Not Started | 0 - None
5.2 a-d | Policy - content | The information security policy must suit the organisation's purpose, contain or frame the security objectives, commit to meeting applicable requirements, and commit to continual improvement. | A short policy (2-4 pages) that a non-specialist can read, containing all four elements explicitly. | Information Security Policy, approved and dated | M1 - Mandate & Scope | YES - mandatory | Not Started | 0 - None
5.2 e-g | Policy - availability and communication | The policy must exist as documented information, be communicated inside the organisation, and be available to interested parties where appropriate. | Policy published where staff can find it, acknowledged by employees, and a public or on-request version available to customers. | Intranet link; acknowledgement records; customer-facing policy summary | M1 - Mandate & Scope | YES - mandatory | Not Started | 0 - None
5.3 | Organizational roles, responsibilities and authorities | Assign and communicate responsibility and authority for the ISMS conforming to the standard and for reporting its performance to top management. | Named individuals (or roles) for ISMS owner, risk owners, control owners, incident lead, internal audit - communicated and understood. | RACI chart; job descriptions; ISMS org chart; appointment letters | M1 - Mandate & Scope | No (but expected) | Not Started | 0 - None
6.1.1 | Actions to address risks and opportunities | Using your context and interested-party analysis, work out what risks and opportunities need addressing so the ISMS achieves its results, prevents undesired effects and improves - then plan and evaluate actions for them. | A documented determination of ISMS-level risks and opportunities (distinct from information security risks to assets), with planned actions integrated into ISMS processes. | ISMS Risks & Opportunities Register; improvement plan | M2 - Risk & Applicability | No (but expected) | Not Started | 0 - None
6.1.2 a | Risk assessment - criteria | Define your risk acceptance criteria and the criteria for performing risk assessments, and write them down. | Explicit scales for likelihood and consequence, a risk matrix, a stated acceptance threshold, and rules for when assessments are triggered. | Risk Management Methodology document with scales and matrix | M2 - Risk & Applicability | YES - mandatory (process) | Not Started | 0 - None
6.1.2 b | Risk assessment - consistency | Make sure that when the assessment is run again, the output can be trusted and set side by side with the previous run. | The same methodology, scales and definitions applied every time, by trained people, with worked examples. | Risk Management Methodology; completed assessments showing consistent scoring | M2 - Risk & Applicability | YES - mandatory (process) | Not Started | 0 - None
6.1.2 c | Risk assessment - identification | Identify the risks to confidentiality, integrity and availability of information within scope, and identify an owner for each risk. | A populated risk register where each entry has a threat, a vulnerability or cause, an affected asset or process, and a named risk owner. | Information Security Risk Register | M2 - Risk & Applicability | YES - results mandatory | Not Started | 0 - None
6.1.2 d | Risk assessment - analysis | Assess the potential consequences and realistic likelihood of each risk and determine its level. | Every risk scored using the defined scales, with the rationale recorded so a third party could follow it. | Risk Register with impact, likelihood, inherent and residual scores | M2 - Risk & Applicability | YES - results mandatory | Not Started | 0 - None
6.1.2 e | Risk assessment - evaluation | Compare each risk against your acceptance criteria and prioritise them for treatment. | Risks sorted, a clear line between accept and treat, and a prioritised treatment queue. | Risk Register with evaluation and priority columns; risk heat map | M2 - Risk & Applicability | YES - results mandatory | Not Started | 0 - None
6.1.3 a-b | Risk treatment - options and controls | Choose treatment options for each unacceptable risk and determine the controls needed to implement them. | For each treated risk: a chosen option (modify / avoid / share / retain) and specific named controls, not vague intentions. | Risk Treatment Plan; Risk Register treatment columns | M2 - Risk & Applicability | YES - process mandatory | Not Started | 0 - None
6.1.3 c | Risk treatment - comparison with Annex A | Compare the controls you determined against the Annex A reference set to confirm you have not missed anything necessary. | A documented pass over all 93 Annex A controls checking each against your determined controls. | Annex A comparison worksheet (this workbook's Annex A tab) | M2 - Risk & Applicability | YES - process mandatory | Not Started | 0 - None
6.1.3 d | Statement of Applicability | Produce an SoA listing the necessary controls, justifying why each is included, stating whether it is implemented, and justifying every exclusion. | A complete SoA covering all 93 Annex A controls plus any additional controls, with a real justification per row - never 'not applicable' with no reason. | Statement of Applicability (approved, version-controlled) | M2 - Risk & Applicability | YES - mandatory | Not Started | 0 - None
6.1.3 e | Risk treatment plan | Formulate a risk treatment plan setting out what will be done, by whom and by when. | A plan with actions, owners, dates, resources and expected residual risk for each treated risk. | Risk Treatment Plan | M2 - Risk & Applicability | YES - mandatory | Not Started | 0 - None
6.1.3 f | Risk owner approval and residual risk acceptance | Get risk owners to approve the risk treatment plan and formally accept the residual risks. | Dated sign-off by each named risk owner, or minuted committee approval covering each residual risk. | Signed Risk Treatment Plan; risk acceptance records; committee minutes | M2 - Risk & Applicability | YES - mandatory | Not Started | 0 - None
6.2 a-g | Information security objectives | Set objectives at relevant functions and levels that are consistent with the policy, measurable where practicable, informed by requirements and risk results, monitored, communicated, updated as needed, and documented. | A handful of real objectives with targets and baselines (e.g. 'close 95% of critical vulnerabilities within 14 days'), not aspirations. | ISMS Objectives & Metrics document; KPI dashboard | M2 - Risk & Applicability | YES - mandatory | Not Started | 0 - None
6.2 h-j | Planning to achieve objectives | For each objective, plan what will be done, what resources are needed, who is responsible, when it will be complete and how results will be evaluated. | Each objective has an owner, a due date, resources and an evaluation method recorded next to it. | Objectives plan with owner/date/resource/evaluation columns | M2 - Risk & Applicability | YES - mandatory | Not Started | 0 - None
6.3 | Planning of changes | When the ISMS needs to change, make the change in a planned way rather than ad hoc. | Significant ISMS changes (scope, structure, major systems) go through a documented consideration of impact before being made. | Change records for ISMS changes; management review minutes; ISMS change log | M5 - Operate & Evidence | No (but expected) | Not Started | 0 - None
7.1 | Resources | Determine and provide the resources the ISMS needs to be established, implemented, maintained and improved. | Budget, people, tools and time identified and provided - with evidence the ask was made and answered. | Resource plan; budget approval; headcount records; tool licences | M3 - Core Documentation | No | Not Started | 0 - None
7.2 a-c | Competence | Determine the competence needed for people whose work affects security performance, ensure they have it, and act to close gaps. | A competence matrix per security-relevant role, with gaps tracked to training, hiring or contracting. | Competence matrix; training plan; certifications; CVs | M3 - Core Documentation | No | Not Started | 0 - None
7.2 d | Competence - evidence retained | Keep documented evidence of competence. | Certificates, training completion records and CVs held on file and retrievable at audit. | Training records; certificates; evidence-of-competence register | M3 - Core Documentation | YES - mandatory | Not Started | 0 - None
7.3 | Awareness | Ensure people doing work under your control know the security policy, how they contribute to the ISMS, and what happens if they do not conform. | Awareness training covering all three points, delivered on induction and refreshed, with completion tracked - including contractors. | Awareness programme; training content; completion reports; induction pack | M5 - Operate & Evidence | No (but records expected) | Not Started | 0 - None
7.4 | Communication | Determine what you need to communicate about the ISMS, when, with whom and how. | A short communication plan covering internal and external audiences, triggers, channels and owners - including breach notification routes. | ISMS Communication Plan | M3 - Core Documentation | No (but expected) | Not Started | 0 - None
7.5.1 | Documented information - general | Hold the documented information the standard requires plus whatever else you determine is needed for the ISMS to work. | A controlled master list of ISMS documents and records, mapped to the clauses that require them. | ISMS Document Register / Master List | M3 - Core Documentation | YES - mandatory | Not Started | 0 - None
7.5.2 | Creating and updating documented information | When creating or updating documents, ensure appropriate identification, description, format, media, and review and approval. | Every ISMS document carries a title, ID, version, date, owner, approver and classification. A defined review and approval route exists. | Document template with header block; approval records; document control procedure | M3 - Core Documentation | YES - mandatory | Not Started | 0 - None
7.5.3 a-b | Control of documented information - availability and protection | Make sure documents are available where and when they are needed, and properly protected against being disclosed, misused or altered. | Documents stored in a controlled repository with access permissions, backup and version history. | Repository permission report; backup evidence; classification labels | M3 - Core Documentation | YES - mandatory | Not Started | 0 - None
7.5.3 c | Control of documented information - lifecycle | Address distribution, access, retrieval, use, storage, preservation, change control, retention and disposition - including documents of external origin. | A document control procedure covering the full lifecycle, plus retention schedule, plus a register of external documents (standards, laws, contracts). | Document Control Procedure; retention schedule; external documents register | M3 - Core Documentation | YES - mandatory | Not Started | 0 - None
8.1 | Operational planning and control | Run the processes the ISMS depends on under proper control: work out what they are, put them into effect, set criteria for how they should operate, govern them against those criteria, keep enough records to be confident they ran as intended, manage deliberate changes, review the fallout from changes you did not intend, and govern processes, products and services obtained from outside. | Security operations run to documented procedures with defined criteria, and outsourced/cloud processes are governed and evidenced. | Operating procedures; change records; supplier oversight records; process KPI reports | M5 - Operate & Evidence | YES - mandatory (to extent necessary) | Not Started | 0 - None
8.2 | Information security risk assessment (operational) | Perform risk assessments at planned intervals and whenever significant changes are proposed or occur, and keep the results. | A defined cadence (e.g. annual full, quarterly review) plus triggered assessments for major change, with dated outputs. | Dated risk assessment reports; risk register change history | M5 - Operate & Evidence | YES - mandatory | Not Started | 0 - None
8.3 | Information security risk treatment (operational) | Implement the risk treatment plan and keep documented evidence of the results. | Treatment actions tracked to closure with evidence attached, and residual risk re-scored after implementation. | Risk Treatment Plan with status/closure evidence; residual risk records | M5 - Operate & Evidence | YES - mandatory | Not Started | 0 - None
9.1 a-c | Monitoring and measurement - what and how | Determine what needs to be monitored and measured, the methods used to get valid results, and when it will be done. | A measurement plan naming each metric, its formula, data source, frequency and target. | Measurement plan / metrics definition sheet | M5 - Operate & Evidence | YES - mandatory (results) | Not Started | 0 - None
9.1 d-e | Monitoring and measurement - analysis | Determine when results are analysed and evaluated and by whom, and keep the evidence. | Regular reporting cycle with a named analyst/owner and a forum where results are discussed and acted on. | Metrics reports; security committee minutes; dashboards | M5 - Operate & Evidence | YES - mandatory (results) | Not Started | 0 - None
9.2.1 | Internal audit - general | Conduct internal audits at planned intervals to check the ISMS conforms to your own requirements and to the standard, and is effectively implemented and maintained. | At least one full-coverage internal audit cycle completed before certification, covering all clauses and applicable controls. | Internal audit reports; audit evidence files | M6 - Audit & Certify | YES - mandatory | Not Started | 0 - None
9.2.2 a-b | Internal audit programme | Set up and keep running an audit programme that states how often audits happen, what methods are used, who is responsible, how they are planned and how results are reported - weighted by how important each area is and what earlier audits found. Each individual audit then needs its own stated criteria and scope. | A multi-period audit programme (usually annual or three-year) plus individual audit plans with scope and criteria. | Internal Audit Programme; individual audit plans | M6 - Audit & Certify | YES - mandatory | Not Started | 0 - None
9.2.2 c-d | Internal audit - auditor objectivity and reporting | Select auditors and conduct audits so the process is objective and impartial, and report results to relevant management. | Auditors do not audit their own work; a documented independence statement; findings formally reported. | Auditor independence declarations; audit reports with distribution list | M6 - Audit & Certify | YES - mandatory | Not Started | 0 - None
9.2.2 e | Internal audit - evidence retained | Keep documented information as evidence of the audit programme and its results. | Programme, plans, working papers, findings and closure evidence all retained. | Audit file: programme, plans, checklists, reports, CAPA records | M6 - Audit & Certify | YES - mandatory | Not Started | 0 - None
9.3.1 | Management review - general | Top management must review the ISMS at planned intervals to confirm it remains suitable, adequate and effective. | At least one full management review completed before certification, chaired by top management, with attendance recorded. | Management Review minutes with attendance | M6 - Audit & Certify | YES - mandatory | Not Started | 0 - None
9.3.2 a-f | Management review - inputs | The review must consider: prior action status; changes in external and internal issues; changes in interested-party needs; security performance feedback (nonconformities and corrective actions, monitoring results, audit results, objective achievement); interested-party feedback; risk assessment results and treatment plan status; and improvement opportunities. | An agenda that explicitly walks every required input, with data packs attached - a generic 'security update' will fail audit. | Management Review agenda, pack and minutes mapped to each required input | M6 - Audit & Certify | YES - mandatory | Not Started | 0 - None
9.3.3 | Management review - results | The review outputs must include decisions on continual improvement and any need to change the ISMS, and be documented. | Minuted decisions with owners and dates, tracked to closure and revisited at the next review. | Management Review minutes with decision/action log | M6 - Audit & Certify | YES - mandatory | Not Started | 0 - None
10.1 | Continual improvement | Keep making the ISMS better over time - a better fit for the organisation, sufficient for what it faces, and more effective at delivering its intended results. | A live improvement log fed by audits, incidents, metrics, reviews and staff suggestions - with things actually closing. | Continual Improvement Plan / improvement register | M6 - Audit & Certify | No (but expected) | Not Started | 0 - None
10.2 a | Nonconformity - reaction | When a nonconformity occurs, react to it: take action to control and correct it and deal with the consequences. | Immediate containment and correction recorded separately from root-cause action. | Nonconformity records showing correction taken | M6 - Audit & Certify | YES - mandatory | Not Started | 0 - None
10.2 b-c | Nonconformity - root cause and corrective action | Evaluate whether action is needed to eliminate the cause so it does not recur: review the nonconformity, determine its causes, check whether similar ones exist or could occur - then implement the action needed. | A root cause method actually applied (5 Whys, fishbone) and a check for the same weakness elsewhere. | CAPA records with root cause analysis and extent-of-condition check | M6 - Audit & Certify | YES - mandatory | Not Started | 0 - None
10.2 d-f | Nonconformity - effectiveness and records | Review the effectiveness of corrective actions, change the ISMS if necessary, keep corrective actions proportionate to the effects, and retain records of the nonconformities, actions taken and results. | Each closed action has a dated effectiveness check by someone other than the person who fixed it. | Nonconformity & Corrective Action Log with effectiveness review column | M6 - Audit & Certify | YES - mandatory | Not Started | 0 - None

## 03 Annex A and SoA
ANNEX A CONTROLS AND STATEMENT OF APPLICABILITY
All 93 controls. Columns J to L together satisfy the mandatory SoA requirement of Clause 6.1.3 d.
Ref | Theme | Control title | Control type | Information security properties | Cybersecurity concepts | Operational capabilities | Security domains | Requirement in plain English | What good looks like | Typical evidence | Milestone | Applicable? (SoA) | Justification for inclusion (SoA) | Risk IDs this control treats | Reason for exclusion (SoA) | Justification for exclusion - detail | Status | How it is implemented (SoA) | Maturity | Control owner | Target date | Evidence reference / location | Notes and gaps
A.5.1 | Organizational | Policies for information security | Preventive | Confidentiality, Integrity, Availability | Identify | Governance | Governance and Ecosystem, Resilience | Maintain a top-level security policy and a set of topic policies. Each must be signed off by management, published where people can find it, actively pushed out to those it covers, confirmed as seen by them, and revisited on a set cycle or after anything significant changes. | One short top-level policy plus a set of topic policies. Every policy has an owner, approval date, review date and version. Staff acknowledgement is tracked. | Approved policy set; approval records; intranet publication; acknowledgement report; review log | M3 - Core Documentation | Yes | Risk assessment | R-004, R-011 |  |  | Implemented | Top-level Information Security Policy plus 11 topic policies approved by the CEO on [DATE], published on the intranet, acknowledged by all staff at induction and annually. | 3 - Defined | ISMS Manager |  | SharePoint > ISMS > 01 Policies | EXAMPLE ROW - shows the expected level of detail. Overwrite with your own.
A.5.2 | Organizational | Information security roles and responsibilities | Preventive | Confidentiality, Integrity, Availability | Identify | Governance | Governance and Ecosystem, Protection, Resilience | Define and allocate information security responsibilities across the organisation according to your own needs. | Every security duty has a named role. Documented in job descriptions and a RACI, not only in someone's head. | RACI chart; job descriptions; appointment records; org chart | M1 - Mandate & Scope | Yes |  |  |  |  | Not Started |  | 0 - None
A.5.3 | Organizational | Segregation of duties | Preventive | Confidentiality, Integrity, Availability | Protect | Governance, Identity and access management | Governance and Ecosystem | Separate conflicting duties and areas of responsibility so no single person can cause and conceal harm unchecked. | Identified toxic combinations (e.g. developer deploying to production unreviewed, requester approving own access) with either separation or documented compensating controls. | Segregation of duties matrix; access review evidence; approval workflows; compensating control notes | M4 - Control Build-out | Yes |  |  |  |  | Not Started |  | 0 - None
A.5.4 | Organizational | Management responsibilities | Preventive | Confidentiality, Integrity, Availability | Identify | Governance | Governance and Ecosystem | Require managers to make their people apply information security in line with policies and procedures. | Security expectations written into management responsibilities and reinforced at induction and in performance conversations. | Manager briefing pack; job descriptions; performance objectives; policy acknowledgement | M3 - Core Documentation | Yes |  |  |  |  | Not Started |  | 0 - None
A.5.5 | Organizational | Contact with authorities | Preventive, Corrective | Confidentiality, Integrity, Availability | Identify, Protect, Respond, Recover | Governance | Defence, Resilience | Establish and maintain contact with relevant authorities and know when and how to reach them. | A maintained contact list covering data protection authority, law enforcement, sector regulator and national CERT, with notification triggers and deadlines documented. | Authority contact list; incident procedure with notification triggers; evidence of prior contact | M4 - Control Build-out | Yes |  |  |  |  | Not Started |  | 0 - None
A.5.6 | Organizational | Contact with special interest groups | Preventive, Corrective | Confidentiality, Integrity, Availability | Protect, Respond, Recover | Governance | Defence | Maintain contact with security-specialist groups, forums and professional associations. | Active memberships or subscriptions (ISACs, CERT feeds, vendor advisory lists) with named people who monitor them. | Membership records; subscription list; meeting/webinar attendance | M4 - Control Build-out | Yes |  |  |  |  | Not Started |  | 0 - None
A.5.7 | Organizational | Threat intelligence | Preventive, Detective, Corrective | Confidentiality, Integrity, Availability | Identify, Detect, Respond | Threat and vulnerability management | Defence, Resilience | Collect and analyse information about security threats and turn it into action. | Defined sources, a person who reviews them on a cadence, and a route from intelligence into vulnerability management, detection rules and risk assessment. | Threat intelligence procedure; source list; threat briefings; tickets raised from intel | M4 - Control Build-out | Yes |  |  |  |  | Not Started |  | 0 - None
A.5.8 | Organizational | Information security in project management | Preventive | Confidentiality, Integrity, Availability | Identify, Protect | Governance | Governance and Ecosystem, Protection | Build information security into project management, for all types of project. | Security requirements, risk assessment and a sign-off gate present in the project lifecycle. Applies to non-IT projects too. | Project methodology with security gates; project security risk assessments; gate sign-offs | M4 - Control Build-out | Yes |  |  |  |  | Not Started |  | 0 - None
A.5.9 | Organizational | Inventory of information and other associated assets | Preventive | Confidentiality, Integrity, Availability | Identify | Asset management | Governance and Ecosystem, Protection | Maintain an inventory of information and associated assets, including who owns each one. | A live inventory covering information sets, applications, infrastructure, endpoints, cloud services and suppliers - each with a named owner and classification. | Asset inventory / CMDB export; owner assignments; reconciliation evidence | M2 - Risk & Applicability | Yes |  |  |  |  | Not Started |  | 0 - None
A.5.10 | Organizational | Acceptable use of information and other associated assets | Preventive | Confidentiality, Integrity, Availability | Protect | Asset management | Protection | Set and communicate rules for the acceptable use and handling of information and assets. | An acceptable use policy people have actually read and accepted, covering BYOD, personal use, AI tools, removable media and social media. | Acceptable Use Policy; acceptance records; handling rules per classification | M3 - Core Documentation | Yes |  |  |  |  | Not Started |  | 0 - None
A.5.11 | Organizational | Return of assets | Preventive | Confidentiality, Integrity, Availability | Protect | Asset management | Protection | Ensure people return organisational assets when their employment, contract or agreement ends or changes. | An offboarding checklist covering laptops, phones, tokens, keys, cards, documents and cloud data, with confirmation recorded. | Offboarding checklist; signed asset return forms; leaver register | M4 - Control Build-out | Yes |  |  |  |  | Not Started |  | 0 - None
A.5.12 | Organizational | Classification of information | Preventive | Confidentiality, Integrity, Availability | Identify | Information protection | Protection, Defence | Classify information based on confidentiality, integrity, availability and interested-party requirements. | A simple scheme (typically 3-4 levels) with clear examples, applied to real information sets and reflected in the asset inventory. | Classification scheme; classified asset inventory; worked examples | M3 - Core Documentation | Yes |  |  |  |  | Not Started |  | 0 - None
A.5.13 | Organizational | Labelling of information | Preventive | Confidentiality, Integrity, Availability | Protect | Information protection | Defence, Protection | Have and apply a procedure for labelling information in line with the classification scheme. | Labelling rules for documents, email, media and systems - ideally enforced by tooling, at minimum by template headers and footers. | Labelling procedure; document templates; labelling tool configuration; sample labelled artefacts | M4 - Control Build-out | Yes |  |  |  |  | Not Started |  | 0 - None
A.5.14 | Organizational | Information transfer | Preventive | Confidentiality, Integrity, Availability | Protect | Asset management, Information protection | Protection | Put rules, procedures and agreements in place for transferring information inside the organisation and with external parties. | Rules, procedures and agreements covering all three modes of transfer that the control addresses: electronic transfer, transfer on physical storage media, and verbal transfer. Approved channels defined per classification, agreements in place for transfers with external parties, protection against interception and unauthorised access in transit, and a clear prohibition on unapproved routes. | Information transfer policy covering electronic, physical and verbal transfer; approved channel list; transfer agreements with external parties; encryption configuration; courier and media-in-transit records | M4 - Control Build-out | Yes |  |  |  |  | Not Started |  | 0 - None
A.5.15 | Organizational | Access control | Preventive | Confidentiality, Integrity, Availability | Protect | Identity and access management | Protection | Establish and implement rules controlling physical and logical access to information and assets, based on business and security requirements. | An access control policy built on least privilege and need-to-know, with role-based access defined and applied consistently. | Access Control Policy; role/permission matrix; access request workflow | M4 - Control Build-out | Yes |  |  |  |  | Not Started |  | 0 - None
A.5.16 | Organizational | Identity management | Preventive | Confidentiality, Integrity, Availability | Protect | Identity and access management | Protection | Manage the full lifecycle of identities. | One authoritative identity source, unique IDs per person, controlled creation and removal, and a documented approach to shared and service accounts. | Identity lifecycle procedure; joiner/mover/leaver records; shared account register; IdP configuration | M4 - Control Build-out | Yes |  |  |  |  | Not Started |  | 0 - None
A.5.17 | Organizational | Authentication information | Preventive | Confidentiality, Integrity, Availability | Protect | Identity and access management | Protection | Control the allocation and management of authentication information such as passwords, keys and tokens. | A password/secrets standard, secure initial credential distribution, a password manager or vault, and MFA where warranted. | Password standard; MFA coverage report; secrets vault configuration; credential issuance procedure | M4 - Control Build-out | Yes |  |  |  |  | Not Started |  | 0 - None
A.5.18 | Organizational | Access rights | Preventive | Confidentiality, Integrity, Availability | Protect | Identity and access management | Protection | Provision, review, modify and remove access rights in line with the access control policy. | Access granted only on documented approval, revoked promptly on leaving, and reviewed periodically by system owners with evidence of action taken. | Access request approvals; leaver revocation logs; periodic access review records with remediation | M4 - Control Build-out | Yes |  |  |  |  | Not Started |  | 0 - None
A.5.19 | Organizational | Information security in supplier relationships | Preventive | Confidentiality, Integrity, Availability | Identify | Supplier relationships security | Governance and Ecosystem, Protection | Define and implement processes to manage the security risks that come with using suppliers' products and services. | A supplier register with risk tiering, and security due diligence proportionate to tier before onboarding. | Supplier security policy; supplier register with tiers; due diligence questionnaires; assessment reports | M4 - Control Build-out | Yes |  |  |  |  | Not Started |  | 0 - None
A.5.20 | Organizational | Addressing information security within supplier agreements | Preventive | Confidentiality, Integrity, Availability | Identify | Supplier relationships security | Governance and Ecosystem, Protection | Establish and agree relevant security requirements with each supplier, according to the type of relationship. | Standard security schedule / DPA clauses in contracts covering confidentiality, incident notification, subprocessors, audit rights, return and deletion of data. | Contract security schedule template; executed contracts; DPAs; clause compliance checklist | M4 - Control Build-out | Yes |  |  |  |  | Not Started |  | 0 - None
A.5.21 | Organizational | Managing information security in the ICT supply chain | Preventive | Confidentiality, Integrity, Availability | Identify | Supplier relationships security | Governance and Ecosystem, Protection | Define and implement processes to manage security risks in the ICT products and services supply chain. | Requirements flowed down to subcontractors, component provenance considered, and known ICT supply chain risks (software dependencies, hardware sourcing) assessed. | ICT supply chain requirements; subcontractor flow-down clauses; SBOM or dependency inventory | M4 - Control Build-out | Yes |  |  |  |  | Not Started |  | 0 - None
A.5.22 | Organizational | Monitoring, review and change management of supplier services | Preventive | Confidentiality, Integrity, Availability | Identify | Supplier relationships security, Information security assurance | Governance and Ecosystem, Protection, Defence | Regularly monitor, review, evaluate and manage changes to suppliers' security practices and service delivery. | Scheduled supplier reviews with evidence (assurance reports, SLA performance, incident history) and a route for handling supplier-side changes. | Supplier review minutes; SOC 2 / ISO certificates on file; SLA reports; supplier change notifications | M5 - Operate & Evidence | Yes |  |  |  |  | Not Started |  | 0 - None
A.5.23 | Organizational | Information security for use of cloud services | Preventive | Confidentiality, Integrity, Availability | Protect | Supplier relationships security | Governance and Ecosystem, Protection | Establish processes for acquiring, using, managing and exiting cloud services in line with your security requirements. | A cloud policy covering approval of new services, shared responsibility understanding, configuration baselines and a documented exit plan per critical service. | Cloud usage policy; approved cloud service register; shared responsibility matrix; exit plans | M4 - Control Build-out | Yes |  |  |  |  | Not Started |  | 0 - None
A.5.24 | Organizational | Information security incident management planning and preparation | Corrective | Confidentiality, Integrity, Availability | Respond, Recover | Governance, Information security event management | Defence | Plan and prepare for incident management by defining processes, roles and responsibilities in advance. | Roles and responsibilities determined and communicated to internal and external interested parties. A common method for reporting events with a stated point of contact. Two linked processes: incident management (administration, documentation, detection, triage, prioritisation, analysis, communication, coordination) and incident response (assessing, responding, learning). Only competent trained people handle incidents, with documented procedures and periodic training. Objectives and priorities agreed with management, including resolution timeframes tied to severity. A plan built around several scenarios, running from evaluation of an event through classification, escalation, possible crisis and continuity activation, controlled recovery, and communication to internal and external parties. | Incident Response Plan covering multiple scenarios; severity matrix with agreed resolution timeframes; contact list and point of contact; role definitions; responder training and competence records; tabletop exercise record | M4 - Control Build-out | Yes |  |  |  |  | Not Started |  | 0 - None
A.5.25 | Organizational | Assessment and decision on information security events | Detective | Confidentiality, Integrity, Availability | Detect, Respond | Information security event management | Defence | Assess security events and decide whether they should be classified as incidents. | A documented triage step with criteria, applied consistently and recorded in the ticketing system. | Triage criteria; event/incident register showing classification decisions | M5 - Operate & Evidence | Yes |  |  |  |  | Not Started |  | 0 - None
A.5.26 | Organizational | Response to information security incidents | Corrective | Confidentiality, Integrity, Availability | Respond, Recover | Information security event management | Defence | Respond to incidents according to documented procedures. | Incidents worked through containment, eradication and recovery with actions and timings recorded against the plan. | Incident tickets with timeline; post-incident reports; evidence of plan being followed | M5 - Operate & Evidence | Yes |  |  |  |  | Not Started |  | 0 - None
A.5.27 | Organizational | Learning from information security incidents | Preventive | Confidentiality, Integrity, Availability | Identify, Protect | Information security event management | Defence | Use knowledge from incidents to strengthen and improve controls. | Post-incident reviews producing improvement actions that are tracked to closure and fed into risk assessment and awareness content. | Post-incident review reports; improvement actions in the CAPA log; updated procedures | M5 - Operate & Evidence | Yes |  |  |  |  | Not Started |  | 0 - None
A.5.28 | Organizational | Collection of evidence | Corrective | Confidentiality, Integrity, Availability | Detect, Respond | Information security event management | Defence | Establish and implement procedures for identifying, collecting, acquiring and preserving evidence relating to security events. | A forensic readiness procedure covering chain of custody, imaging, log preservation and when to involve external specialists or law enforcement. | Evidence handling procedure; chain of custody forms; forensic retainer contract | M4 - Control Build-out | Yes |  |  |  |  | Not Started |  | 0 - None
A.5.29 | Organizational | Information security during disruption | Preventive | Confidentiality, Integrity, Availability | Protect, Respond | Continuity | Protection, Resilience | Work out in advance how security will be held to an acceptable standard while the business is disrupted. | Continuity plans that explicitly address security in degraded/failover mode, so workarounds do not bypass controls. | Business Continuity Plan with security section; crisis procedures; exercise reports | M4 - Control Build-out | Yes |  |  |  |  | Not Started |  | 0 - None
A.5.30 | Organizational | ICT readiness for business continuity | Corrective | Availability | Respond | Continuity | Resilience | Build, keep up and exercise the ICT recovery capability so that it actually meets the continuity targets the business has set. | ICT continuity requirements derived from a business impact analysis that assesses impact over time, identifies prioritised activities, assigns each an RTO, and determines the resources - including ICT services - needed to support them, with RPOs for the information involved. Continuity strategies chosen covering before, during and after disruption. Plans developed, approved by management and regularly exercised, stating the performance and capacity specifications needed, the RTO for each prioritised ICT service and how it is restored, and the RPO for each prioritised resource and how the information is restored. An organisational structure with the responsibility, authority and competence to respond. | BIA with impact-over-time analysis and prioritised activities; ICT continuity plans approved by management; performance and capacity specifications; DR test and exercise reports showing actual against target RTO and RPO | M4 - Control Build-out | Yes |  |  |  |  | Not Started |  | 0 - None
A.5.31 | Organizational | Legal, statutory, regulatory and contractual requirements | Preventive | Confidentiality, Integrity, Availability | Identify | Legal and compliance | Governance and Ecosystem, Protection | Work out which laws, regulations and contract terms bear on your information security, write each one down alongside how you satisfy it, and keep that record current. | A legal register naming each obligation, its source, the owner and the control that satisfies it - reviewed at least annually. | Legal & Regulatory Register; compliance mapping; legal review records | M3 - Core Documentation | Yes |  |  |  |  | Not Started |  | 0 - None
A.5.32 | Organizational | Intellectual property rights | Preventive | Confidentiality, Integrity, Availability | Identify | Legal and compliance | Governance and Ecosystem | Implement procedures to protect intellectual property rights. | Software licence compliance tracked, open-source licence obligations understood, and rules on third-party content and AI-generated material. | IP policy; software licence register; SCA/licence scan reports | M4 - Control Build-out | Yes |  |  |  |  | Not Started |  | 0 - None
A.5.33 | Organizational | Protection of records | Preventive | Confidentiality, Integrity, Availability | Identify, Protect | Legal and compliance, Asset management, Information protection | Defence | Protect records against loss, destruction, falsification, unauthorised access and unauthorised release. | A retention schedule per record type, storage with integrity protection, and controlled disposal. | Records retention schedule; storage controls; disposal certificates; access restrictions | M4 - Control Build-out | Yes |  |  |  |  | Not Started |  | 0 - None
A.5.34 | Organizational | Privacy and protection of PII | Preventive | Confidentiality, Integrity, Availability | Identify, Protect | Information protection, Legal and compliance | Protection | Identify and meet the requirements for preserving privacy and protecting personal data under applicable law and contract. | A record of processing activities, lawful bases, DPIAs where required, data subject rights process, and privacy notices. | RoPA; privacy notices; DPIAs; DSR procedure and log; DPA register | M4 - Control Build-out | Yes |  |  |  |  | Not Started |  | 0 - None
A.5.35 | Organizational | Independent review of information security | Preventive, Corrective | Confidentiality, Integrity, Availability | Identify, Protect | Information security assurance | Governance and Ecosystem | Review the organisation's approach to managing information security independently, at planned intervals and after significant change. | Independent internal audit, or an external review, covering the ISMS and its controls - with findings reported to management. | Internal audit reports; external assessment reports; auditor independence statements | M6 - Audit & Certify | Yes |  |  |  |  | Not Started |  | 0 - None
A.5.36 | Organizational | Compliance with policies, rules and standards for information security | Preventive | Confidentiality, Integrity, Availability | Identify, Protect | Legal and compliance, Information security assurance | Governance and Ecosystem | Regularly review whether information processing and procedures actually comply with your own policies, rules and standards. | Managers and control owners perform periodic compliance checks in their areas, with results recorded and gaps remediated. | Compliance check schedule and results; technical compliance scan reports; remediation tickets | M5 - Operate & Evidence | Yes |  |  |  |  | Not Started |  | 0 - None
A.5.37 | Organizational | Documented operating procedures | Preventive, Corrective | Confidentiality, Integrity, Availability | Protect, Recover | Asset management, Physical security, Application security, Secure configuration, Identity and access management, Threat and vulnerability management, Continuity, Information security event management | Defence | Document the operating procedures for information processing facilities and make them available to those who need them. | Runbooks and SOPs for backup, patching, user administration, monitoring, incident handling and change - current and accessible. | Runbook library; SOPs; procedure review dates; access evidence | M3 - Core Documentation | Yes |  |  |  |  | Not Started |  | 0 - None
A.6.1 | People | Screening | Preventive | Confidentiality, Integrity, Availability | Protect | Human resource security | Governance and Ecosystem | Carry out background verification on candidates before they join, and on an ongoing basis where appropriate. Proportionality is judged against business requirements, the classification of the information the person will access, and the perceived risks - not simply job title. Must be lawful and ethical in each jurisdiction. | A screening standard tied to role risk (identity, right to work, references, criminal record, credit or clearance for sensitive roles), applied to contractors too. | Screening policy; completed screening records; contractor screening attestations | M4 - Control Build-out | Yes |  |  |  |  | Not Started |  | 0 - None
A.6.2 | People | Terms and conditions of employment | Preventive | Confidentiality, Integrity, Availability | Protect | Human resource security | Governance and Ecosystem | State the personnel's and the organisation's information security responsibilities in the employment contract. | Standard security and confidentiality clauses in every employment and contractor agreement, referencing the policy set. | Employment contract template; signed contracts; contractor agreements | M4 - Control Build-out | Yes |  |  |  |  | Not Started |  | 0 - None
A.6.3 | People | Information security awareness, education and training | Preventive | Confidentiality, Integrity, Availability | Protect | Human resource security | Governance and Ecosystem | Give personnel and relevant interested parties appropriate awareness, education and training, updated regularly, including on policies and procedures relevant to their role. | Induction training plus at least annual refreshers, role-specific training for higher-risk roles (developers, admins, finance), and phishing simulation with follow-up. | Awareness plan; training content; completion reports; phishing simulation results | M5 - Operate & Evidence | Yes |  |  |  |  | Not Started |  | 0 - None
A.6.4 | People | Disciplinary process | Preventive, Corrective | Confidentiality, Integrity, Availability | Protect, Respond | Human resource security | Governance and Ecosystem | Have a formalised and communicated disciplinary process to act against people who violate information security policy. | A documented process, referenced in the security policy, that staff have been told about - consistent with employment law. | Disciplinary policy; communication evidence; anonymised case records | M3 - Core Documentation | Yes |  |  |  |  | Not Started |  | 0 - None
A.6.5 | People | Responsibilities after termination or change of employment | Preventive | Confidentiality, Integrity, Availability | Protect | Human resource security, Asset management | Governance and Ecosystem | Define, enforce and communicate the security responsibilities that continue after employment ends or changes. | Ongoing confidentiality obligations stated in contract and restated at exit interview; access removed on role change, not just on exit. | Contract clauses; exit interview checklist; mover access change records | M4 - Control Build-out | Yes |  |  |  |  | Not Started |  | 0 - None
A.6.6 | People | Confidentiality or non-disclosure agreements | Preventive | Confidentiality | Protect | Human resource security, Information protection, Supplier relationships security | Governance and Ecosystem | Identify, document, regularly review and require signature of confidentiality or non-disclosure agreements reflecting your needs. | An NDA register covering employees, contractors and third parties, with a review cycle and current signed copies. | NDA template; NDA register; signed agreements; review log | M4 - Control Build-out | Yes |  |  |  |  | Not Started |  | 0 - None
A.6.7 | People | Remote working | Preventive | Confidentiality, Integrity, Availability | Protect | Asset management, Information protection, Physical security, System and network security | Protection | Implement security measures for people working outside the organisation's premises. | A remote work standard covering device security, VPN or zero-trust access, home network guidance, physical/visual privacy and travel rules. | Remote working policy; VPN/ZTNA configuration; device compliance report | M4 - Control Build-out | Yes |  |  |  |  | Not Started |  | 0 - None
A.6.8 | People | Information security event reporting | Detective | Confidentiality, Integrity, Availability | Detect | Information security event management | Defence | Give people a way to flag security events they have seen or suspect, quickly and without friction. | An obvious, low-friction channel (button, address, hotline) that people know about and are not punished for using. | Reporting procedure; reporting channel screenshot; awareness material; report volume statistics | M5 - Operate & Evidence | Yes |  |  |  |  | Not Started |  | 0 - None
A.7.1 | Physical | Physical security perimeters | Preventive | Confidentiality, Integrity, Availability | Protect | Physical security | Protection | Define and use security perimeters to protect areas containing information and associated assets. | Documented perimeters (site, building, floor, secure room) with appropriate physical barriers at each. | Site plans with perimeters marked; photos; landlord/facility agreements | M4 - Control Build-out | Yes |  |  |  |  | Not Started |  | 0 - None
A.7.2 | Physical | Physical entry | Preventive | Confidentiality, Integrity, Availability | Protect | Physical security | Protection | Protect secure areas with appropriate entry controls and access points. | Entry restricted to authorised people only, with access rights granted, reviewed and revoked on a defined cycle and an auditable record of every entry retained. Visitors admitted only for a specific authorised purpose, with identity verified, dates and times recorded, and escorting throughout. Delivery and loading areas controlled and separated from areas holding information and equipment, so that a delivery driver never needs to enter a secure area. Incoming material inspected for tampering before being moved inside, registered on entry, and segregated from outgoing shipments. | Access control system report and entry records; visitor log with purpose, identity verification and escort; badge issuance and revocation records; delivery area layout; incoming material inspection and registration records; access review evidence | M4 - Control Build-out | Yes |  |  |  |  | Not Started |  | 0 - None
A.7.3 | Physical | Securing offices, rooms and facilities | Preventive | Confidentiality, Integrity, Availability | Protect | Physical security, Asset management | Protection | Design and apply physical security to offices, rooms and facilities. | Sensitive areas not signposted, lockable, and separated from public-accessible space. | Floor plans; photographs; physical security assessment report | M4 - Control Build-out | Yes |  |  |  |  | Not Started |  | 0 - None
A.7.4 | Physical | Physical security monitoring | Preventive, Detective | Confidentiality, Integrity, Availability | Protect, Detect | Physical security | Protection, Defence | Continuously monitor premises for unauthorised physical access. | CCTV and/or intruder alarms covering entry points and sensitive areas, with recordings retained and alarms responded to. | CCTV coverage plan; retention setting; alarm monitoring contract; incident response records | M4 - Control Build-out | Yes |  |  |  |  | Not Started |  | 0 - None
A.7.5 | Physical | Protecting against physical and environmental threats | Preventive | Confidentiality, Integrity, Availability | Protect | Physical security | Protection | Put defences in place against physical and environmental hazards - fire, water, extreme weather, and deliberate attack on the premises. | Threats assessed for each site, with fire suppression, water detection, and siting decisions documented. | Site risk assessment; fire certificates; suppression and detection system records | M4 - Control Build-out | Yes |  |  |  |  | Not Started |  | 0 - None
A.7.6 | Physical | Working in secure areas | Preventive | Confidentiality, Integrity, Availability | Protect | Physical security | Protection | Design and apply security measures for working in secure areas. | Rules on unsupervised working, recording devices, and awareness of who is present in the area. | Secure area working rules; signage; training records | M4 - Control Build-out | Yes |  |  |  |  | Not Started |  | 0 - None
A.7.7 | Physical | Clear desk and clear screen | Preventive | Confidentiality | Protect | Physical security | Protection | Set and enforce rules that keep paper and removable media off unattended desks, and that keep screens locked whenever nobody is at them. | Enforced screen lock timeout via policy configuration, plus periodic clear-desk walkthroughs. | Clear Desk & Clear Screen Policy; MDM/GPO lock settings; walkthrough inspection records | M4 - Control Build-out | Yes |  |  |  |  | Not Started |  | 0 - None
A.7.8 | Physical | Equipment siting and protection | Preventive | Confidentiality, Integrity, Availability | Protect | Physical security, Asset management | Protection | Site and protect equipment securely. | Servers and network gear in locked racks or rooms; screens not visible from public areas; equipment away from environmental hazards. | Rack/room photographs; siting standard; data centre agreement | M4 - Control Build-out | Yes |  |  |  |  | Not Started |  | 0 - None
A.7.9 | Physical | Security of assets off-premises | Preventive | Confidentiality, Integrity, Availability | Protect | Physical security, Asset management | Protection | Protect assets used away from the organisation's premises. | Full-disk encryption, remote wipe, cable locks or equivalent, plus rules for travel and home storage. | Encryption compliance report; MDM policy; off-site asset register; travel guidance | M4 - Control Build-out | Yes |  |  |  |  | Not Started |  | 0 - None
A.7.10 | Physical | Storage media | Preventive | Confidentiality, Integrity, Availability | Protect | Physical security, Asset management | Protection | Manage storage media through acquisition, use, transport and disposal in line with the classification and handling scheme. | Removable media controlled or blocked, encrypted where allowed, tracked in transit, and securely destroyed at end of life. | Media handling procedure; USB control configuration; media register; destruction certificates | M4 - Control Build-out | Yes |  |  |  |  | Not Started |  | 0 - None
A.7.11 | Physical | Supporting utilities | Preventive, Detective | Integrity, Availability | Protect, Detect | Physical security | Protection | Shield processing facilities from loss of power, cooling and the other utilities they depend on. | UPS and/or generator sized and tested, HVAC maintained, with test records. | UPS/generator test records; maintenance contracts; data centre SLA | M4 - Control Build-out | Yes |  |  |  |  | Not Started |  | 0 - None
A.7.12 | Physical | Cabling security | Preventive | Confidentiality, Availability | Protect | Physical security | Protection | Protect cabling carrying power, data and supporting information services from interception, interference and damage. | Cabling in conduit or protected routes, patch panels in locked cabinets, and cable runs documented. | Cabling standard; photographs; cable schedule; data centre specification | M4 - Control Build-out | Yes |  |  |  |  | Not Started |  | 0 - None
A.7.13 | Physical | Equipment maintenance | Preventive | Confidentiality, Integrity, Availability | Protect | Physical security, Asset management | Protection, Resilience | Keep equipment properly maintained so that the information it holds stays available, accurate and private. | A maintenance schedule followed, vendor maintenance supervised, and data protected during off-site repair. | Maintenance schedule and logs; vendor contracts with confidentiality terms; supervision records | M4 - Control Build-out | Yes |  |  |  |  | Not Started |  | 0 - None
A.7.14 | Physical | Secure disposal or re-use of equipment | Preventive | Confidentiality | Protect | Physical security, Asset management | Protection | Verify that equipment containing storage media has sensitive data and licensed software removed or securely overwritten before disposal or re-use. | A documented sanitisation standard, verification per device, and destruction certificates from any third party. | Disposal procedure; sanitisation records per asset tag; destruction certificates | M4 - Control Build-out | Yes |  |  |  |  | Not Started |  | 0 - None
A.8.1 | Technological | User end point devices | Preventive | Confidentiality, Integrity, Availability | Protect | Asset management, Information protection | Protection | Protect whatever information sits on, runs through, or can be reached from laptops, desktops, phones and tablets. | A topic-specific policy covering: which classification levels a device may hold; device registration; physical protection; software versions and automatic updating; restricted software installation; rules for connecting to public and other off-premises networks; access control; storage encryption; malware protection; remote disable, wipe and lockout; backups; removable media and physical port control; and separation of company from personal data on the device. Enforced through configuration management or endpoint tooling rather than by asking. Where information is too sensitive to sit on a device at all, downloading and local storage are disabled. Users are told what is expected of them - lock sessions, care in public places, privacy screens. | Endpoint policy; device register; MDM enrolment and compliance report; encryption report; software installation restriction settings; remote wipe capability evidence; USB and port control configuration; BYOD terms; user awareness content | M4 - Control Build-out | Yes |  |  |  |  | Not Started |  | 0 - None
A.8.2 | Technological | Privileged access rights | Preventive | Confidentiality, Integrity, Availability | Protect | Identity and access management | Protection | Keep administrative rights tightly limited, and govern both how they are handed out and how they get used. | Privileged rights identified per system and allocated on an event-by-event basis, to a separate identity from the user's day-to-day account, on documented approval and only for as long as needed. Competence requirements defined for anyone holding privileged rights, with periodic verification. Generic shared administrator identities avoided; where technically unavoidable they are registered and their use made attributable. Privileged use logged and reviewed frequently, and rights expire rather than persist. | Privileged account register including any generic administrator identities; approval and expiry records; competence evidence for privileged users; PAM configuration; privileged activity logs; privileged access review evidence | M4 - Control Build-out | Yes |  |  |  |  | Not Started |  | 0 - None
A.8.3 | Technological | Information access restriction | Preventive | Confidentiality, Integrity, Availability | Protect | Identity and access management | Protection | Restrict access to information and other associated assets in accordance with the access control policy. | Permissions enforced at application and data level, with default-deny and no broad 'everyone' shares. | Permission reports; share scan results; application role configuration | M4 - Control Build-out | Yes |  |  |  |  | Not Started |  | 0 - None
A.8.4 | Technological | Access to source code | Preventive | Confidentiality, Integrity, Availability | Protect | Application security, Secure configuration | Protection | Control who can view and who can alter source code, build tooling and shared libraries. | Repository access controlled by team, branch protection enforced, and no secrets committed. | Repository access report; branch protection settings; secret scanning results | M4 - Control Build-out | Yes |  |  |  |  | Not Started |  | 0 - None
A.8.5 | Technological | Secure authentication | Preventive | Confidentiality, Integrity, Availability | Protect | Identity and access management | Protection | Implement secure authentication technologies and procedures based on the access restrictions and access control policy. | Authentication technique chosen to match the sensitivity of what is being accessed - multi-factor for all external and privileged access, and biometric or token-based where the risk warrants it. Credentials never displayed on screen as they are entered and never transmitted in clear text. Unsuccessful attempts limited, with lock-out and alerting; both successful and unsuccessful attempts logged. Sessions handled securely with inactivity timeout and re-authentication for sensitive operations. No informative error messages that tell an attacker which half of the credential was wrong. | MFA coverage report; IdP configuration including lockout and session settings; authentication policy; logs of successful and failed authentication attempts; evidence that credentials are not transmitted or stored in clear | M4 - Control Build-out | Yes |  |  |  |  | Not Started |  | 0 - None
A.8.6 | Technological | Capacity management | Preventive, Detective | Integrity, Availability | Identify, Protect, Detect | Continuity | Governance and Ecosystem, Protection | Track how much capacity is being consumed and adjust it against both what is needed now and what will be needed. | Capacity monitored with thresholds and alerts for compute, storage, network and licences, plus forward planning. | Capacity monitoring dashboards; alert configuration; capacity plan; trend reports | M4 - Control Build-out | Yes |  |  |  |  | Not Started |  | 0 - None
A.8.7 | Technological | Protection against malware | Preventive, Detective, Corrective | Confidentiality, Integrity, Availability | Protect, Detect | Information protection | Protection, Defence | Implement protection against malware, supported by user awareness. | Endpoint and email protection deployed to full coverage, kept current, with alerts triaged - reinforced by awareness training. | EDR/AV coverage report; email filtering configuration; detection statistics; awareness content | M4 - Control Build-out | Yes |  |  |  |  | Not Started |  | 0 - None
A.8.8 | Technological | Management of technical vulnerabilities | Preventive | Confidentiality, Integrity, Availability | Identify, Protect | Threat and vulnerability management | Governance and Ecosystem, Protection, Defence | Obtain information about technical vulnerabilities in the systems you use, evaluate your exposure and take appropriate measures. | An accurate software inventory comes first - vendor, product, version, where it is deployed and who owns it - because you cannot track vulnerabilities in software nobody has listed. Then: named responsibility for monitoring, assessment, patching and asset tracking; information sources chosen per technology in use and kept current; authenticated scanning with tooling suited to the platforms; tracking of third-party libraries and dependencies; planned penetration testing by competent authorised people; SLAs by severity that are actually met; patches tested before deployment with a rollback route; and, where no patch exists, documented compensating measures. Suppliers are contractually required to report and disclose vulnerabilities in what they supply. | Vulnerability management procedure with SLAs and named roles; software inventory with versions; scan reports; dependency scan output; penetration test reports and rules of engagement; patch test and rollback records; remediation tickets; SLA compliance metrics; vulnerability disclosure contact point | M4 - Control Build-out | Yes |  |  |  |  | Not Started |  | 0 - None
A.8.9 | Technological | Configuration management | Preventive | Confidentiality, Integrity, Availability | Protect | Secure configuration | Protection | Establish, document, implement, monitor and review the configurations of hardware, software, services and networks. | Hardened baselines (CIS or vendor benchmarks) defined per platform, applied via automation, and drift detected. | Configuration baselines; IaC repository; compliance scan results; drift reports | M4 - Control Build-out | Yes |  |  |  |  | Not Started |  | 0 - None
A.8.10 | Technological | Information deletion | Preventive | Confidentiality | Protect | Information protection, Legal and compliance | Protection | Delete information stored in systems, devices or any other storage media when it is no longer required. | Retention periods defined and technically enforced, with deletion evidenced - including in backups and with cloud providers. | Retention schedule; deletion job configuration; deletion logs; supplier deletion confirmations | M4 - Control Build-out | Yes |  |  |  |  | Not Started |  | 0 - None
A.8.11 | Technological | Data masking | Preventive | Confidentiality | Protect | Information protection | Protection | Use data masking in line with the access control policy and business requirements, taking account of applicable law. | Personal or sensitive data masked, tokenised or pseudonymised in non-production and in interfaces where full values are not needed. | Masking standard; masking tool configuration; non-production data handling procedure | M4 - Control Build-out | Yes |  |  |  |  | Not Started |  | 0 - None
A.8.12 | Technological | Data leakage prevention | Preventive, Detective | Confidentiality | Protect, Detect | Information protection | Protection, Defence | Apply leakage prevention wherever sensitive information is handled - on the systems holding it, across the networks carrying it, and on the devices reaching it. | Controls proportionate to risk: egress restrictions, email DLP rules, USB control, cloud app monitoring - with alerts reviewed. | DLP policy and rules; alert reports; USB control configuration; CASB reports | M4 - Control Build-out | Yes |  |  |  |  | Not Started |  | 0 - None
A.8.13 | Technological | Information backup | Corrective | Integrity, Availability | Recover | Continuity | Protection | Maintain and regularly test backups of information, software and systems in line with an agreed backup policy. | Backups meeting the agreed RPO, stored with an offline or immutable copy, and restore-tested with documented results. | Backup policy; backup job reports; immutability/offline evidence; restore test records | M4 - Control Build-out | Yes |  |  |  |  | Not Started |  | 0 - None
A.8.14 | Technological | Redundancy of information processing facilities | Preventive | Availability | Protect | Continuity, Asset management | Protection, Resilience | Implement information processing facilities with enough redundancy to meet availability requirements. | Redundancy designed to the agreed availability targets, with failover tested rather than assumed. | Architecture diagrams; HA configuration; failover test reports; availability metrics | M4 - Control Build-out | Yes |  |  |  |  | Not Started |  | 0 - None
A.8.15 | Technological | Logging | Detective | Confidentiality, Integrity, Availability | Detect | Information security event management | Protection, Defence | Produce, store, protect and analyse logs recording activities, exceptions, faults and other relevant events. | Defined event types logged across all in-scope systems - user activities, exceptions, faults, access, privilege use, configuration change and security tool alerts - with each entry recording what happened, when, on which system and under which identity. Centralised collection, protection against alteration and deletion including by administrators, restricted and itself-logged access to the logs, and a retention period matched to investigation and legal need. Logs are analysed rather than merely stored, and feed the monitoring activities under A.8.16. | Logging standard defining events and fields; SIEM or log platform source inventory with coverage gaps recorded; retention configuration; log integrity and access controls; evidence that logs are analysed, not just collected | M4 - Control Build-out | Yes |  |  |  |  | Not Started |  | 0 - None
A.8.16 | Technological | Monitoring activities | Detective, Corrective | Confidentiality, Integrity, Availability | Detect, Respond | Information security event management | Defence | Monitor networks, systems and applications for anomalous behaviour and act on the results. | Detection use cases defined, alerts tuned, and a documented route from alert to triage to incident. | Detection rule set; alert triage records; monitoring coverage report; SOC reports | M4 - Control Build-out | Yes |  |  |  |  | Not Started |  | 0 - None
A.8.17 | Technological | Clock synchronization | Detective | Integrity | Protect, Detect | Information security event management | Protection, Defence | Synchronise the clocks of information processing systems to approved time sources. | NTP configured from authoritative sources across all systems, with drift monitored. | NTP configuration standard; time source list; drift monitoring evidence | M4 - Control Build-out | Yes |  |  |  |  | Not Started |  | 0 - None
A.8.18 | Technological | Use of privileged utility programs | Preventive | Confidentiality, Integrity, Availability | Protect | Secure configuration, Application security | Protection | Restrict and tightly control the use of utility programs capable of overriding system and application controls. | Such tools inventoried, restricted to named administrators, and their use logged and reviewed. | Utility program inventory; access restrictions; usage logs; approval records | M4 - Control Build-out | Yes |  |  |  |  | Not Started |  | 0 - None
A.8.19 | Technological | Installation of software on operational systems | Preventive | Confidentiality, Integrity, Availability | Protect | Secure configuration, Application security | Protection | Control how software gets installed on live systems, through both a defined procedure and technical restriction. | Application allow-listing or restricted install rights, a defined approval route for new software, and version control of installed packages. | Software installation policy; allow-list configuration; approved software register; change records | M4 - Control Build-out | Yes |  |  |  |  | Not Started |  | 0 - None
A.8.20 | Technological | Networks security | Preventive, Detective | Confidentiality, Integrity, Availability | Protect, Detect | System and network security | Protection | Secure, manage and control networks and network devices to protect the information in systems and applications. | Documented network architecture, hardened devices, controlled rule bases and periodic firewall rule review. | Network diagrams; device configuration standards; firewall rule review records | M4 - Control Build-out | Yes |  |  |  |  | Not Started |  | 0 - None
A.8.21 | Technological | Security of network services | Preventive | Confidentiality, Integrity, Availability | Protect | System and network security | Protection | Identify, implement and monitor the security mechanisms, service levels and requirements of network services. | Security requirements and SLAs agreed with network service providers and monitored against. | Network service agreements with security terms; SLA reports; monitoring evidence | M4 - Control Build-out | Yes |  |  |  |  | Not Started |  | 0 - None
A.8.22 | Technological | Segregation of networks | Preventive | Confidentiality, Integrity, Availability | Protect | System and network security | Protection | Split the network so that different classes of user, service and system sit in separate zones. | Segmentation between user, server, management, guest and OT/production zones, enforced and documented. | Segmentation design; VLAN/subnet documentation; firewall policy between zones; validation tests | M4 - Control Build-out | Yes |  |  |  |  | Not Started |  | 0 - None
A.8.23 | Technological | Web filtering | Preventive | Confidentiality, Integrity, Availability | Protect | System and network security | Protection | Manage access to external websites to reduce exposure to malicious content. | Category-based filtering with blocked known-bad categories, plus logging and an exception process. | Web filtering configuration; blocked category list; exception register; usage reports | M4 - Control Build-out | Yes |  |  |  |  | Not Started |  | 0 - None
A.8.24 | Technological | Use of cryptography | Preventive | Confidentiality, Integrity, Availability | Protect | Secure configuration | Protection | Set out how encryption is to be used and how keys are to be handled, then apply those rules consistently. | An approved algorithm and key-length standard, encryption in transit and at rest per classification, and a documented key lifecycle. | Cryptographic Controls Policy; key management procedure; certificate inventory; TLS configuration scan | M4 - Control Build-out | Yes |  |  |  |  | Not Started |  | 0 - None
A.8.25 | Technological | Secure development life cycle | Preventive | Confidentiality, Integrity, Availability | Protect | Application security, System and network security | Protection | Write down how software and systems are to be built securely, and hold delivery teams to it. | Security built into each SDLC phase with defined gates, and the rules written down and followed by every delivery team. | Secure SDLC policy; pipeline gate configuration; design review records | M4 - Control Build-out | Yes |  |  |  |  | Not Started |  | 0 - None
A.8.26 | Technological | Application security requirements | Preventive | Confidentiality, Integrity, Availability | Protect | Application security | Protection, Defence | Identify, specify and approve information security requirements when developing or acquiring applications. | A standard security requirements set applied at requirements stage, tailored by application risk, and signed off. | Security requirements checklist per project; approval records; procurement security requirements | M4 - Control Build-out | Yes |  |  |  |  | Not Started |  | 0 - None
A.8.27 | Technological | Secure system architecture and engineering principles | Preventive | Confidentiality, Integrity, Availability | Protect | Application security, System and network security | Protection | Establish, document, maintain and apply principles for engineering secure systems. | Documented principles (defence in depth, least privilege, fail secure, zero trust) applied and evidenced in design reviews. | Security architecture principles document; design review records; reference architectures | M4 - Control Build-out | Yes |  |  |  |  | Not Started |  | 0 - None
A.8.28 | Technological | Secure coding | Preventive | Confidentiality, Integrity, Availability | Protect | Application security, System and network security | Protection | Apply secure coding principles to software development. | Secure coding applied across all three phases the control expects: before coding (a secure baseline, developer competence, prohibited insecure techniques and design patterns), during coding (coding standards for the languages in use, peer review, version control, protection against common vulnerability classes, secure use of third-party components and libraries with their versions tracked), and after coding (testing, review before release, and maintenance of released code). Tooling enforces what it can - branch protection, static analysis, dependency and secret scanning in the pipeline. | Secure coding standard per language; list of prohibited techniques; branch protection settings; SAST, SCA and secret-scanning reports; code review evidence; third-party component inventory with versions; developer training records | M4 - Control Build-out | Yes |  |  |  |  | Not Started |  | 0 - None
A.8.29 | Technological | Security testing in development and acceptance | Preventive | Confidentiality, Integrity, Availability | Identify | Application security, Information security assurance, System and network security | Protection | Define and implement security testing processes in the development lifecycle. | Defined testing per release risk (SAST, DAST, dependency scan, periodic penetration testing), with findings tracked to closure. | Test strategy; scan reports; penetration test reports; remediation tracking | M4 - Control Build-out | Yes |  |  |  |  | Not Started |  | 0 - None
A.8.30 | Technological | Outsourced development | Preventive, Detective | Confidentiality, Integrity, Availability | Identify, Protect, Detect | Application security, Supplier relationships security | Protection | Direct, monitor and review the activities of outsourced system development. | Security requirements in the development contract, right to test, code ownership and escrow, and evidence of oversight. | Development contracts with security clauses; review meeting minutes; acceptance testing records | M4 - Control Build-out | Yes |  |  |  |  | Not Started |  | 0 - None
A.8.31 | Technological | Separation of development, test and production environments | Preventive | Confidentiality, Integrity, Availability | Protect | Application security, System and network security | Protection | Separate and secure development, test and production environments. | Environments logically or physically separated, with distinct credentials and controlled promotion between them. | Environment architecture; access separation evidence; deployment pipeline configuration | M4 - Control Build-out | Yes |  |  |  |  | Not Started |  | 0 - None
A.8.32 | Technological | Change management | Preventive | Confidentiality, Integrity, Availability | Protect | Application security, System and network security | Protection | Put every change to live systems and processing facilities through a controlled change process. | A change process with risk assessment, testing, approval, rollback plan and post-implementation review - including emergency changes. | Change Management Procedure; change records with approvals; CAB minutes; emergency change log | M4 - Control Build-out | Yes |  |  |  |  | Not Started |  | 0 - None
A.8.33 | Technological | Test information | Preventive | Confidentiality, Integrity | Protect | Information protection | Protection | Select, protect and manage test information appropriately. | Production data not used in test, or masked if unavoidable, with approval and deletion after use. | Test data standard; masking evidence; approval records for any production data use | M4 - Control Build-out | Yes |  |  |  |  | Not Started |  | 0 - None
A.8.34 | Technological | Protection of information systems during audit testing | Preventive | Confidentiality, Integrity, Availability | Protect | System and network security, Information protection | Governance and Ecosystem, Protection | Plan and agree audit tests and other assurance activities involving operational systems between the tester and appropriate management. | Audit and penetration testing scoped, scheduled and authorised in writing, with read-only access where possible and rollback arranged. | Audit test plans; written authorisation; rules of engagement for penetration tests; access records | M6 - Audit & Certify | Yes |  |  |  |  | Not Started |  | 0 - None
CC-01 | Custom | [Additional control not in Annex A] | [5 empty] | [Describe the control you determined during risk treatment that Annex A does not cover] |  |  | M4 - Control Build-out | [5 empty] | Not Started |  | 0 - None
CC-02 | Custom | [Additional control not in Annex A] | [5 empty] | [Describe the control you determined during risk treatment that Annex A does not cover] |  |  | M4 - Control Build-out | [5 empty] | Not Started |  | 0 - None
CC-03 | Custom | [Additional control not in Annex A] | [5 empty] | [Describe the control you determined during risk treatment that Annex A does not cover] |  |  | M4 - Control Build-out | [5 empty] | Not Started |  | 0 - None
CC-04 | Custom | [Additional control not in Annex A] | [5 empty] | [Describe the control you determined during risk treatment that Annex A does not cover] |  |  | M4 - Control Build-out | [5 empty] | Not Started |  | 0 - None
CC-05 | Custom | [Additional control not in Annex A] | [5 empty] | [Describe the control you determined during risk treatment that Annex A does not cover] |  |  | M4 - Control Build-out | [5 empty] | Not Started |  | 0 - None
CC-06 | Custom | [Additional control not in Annex A] | [5 empty] | [Describe the control you determined during risk treatment that Annex A does not cover] |  |  | M4 - Control Build-out | [5 empty] | Not Started |  | 0 - None
CC-07 | Custom | [Additional control not in Annex A] | [5 empty] | [Describe the control you determined during risk treatment that Annex A does not cover] |  |  | M4 - Control Build-out | [5 empty] | Not Started |  | 0 - None
CC-08 | Custom | [Additional control not in Annex A] | [5 empty] | [Describe the control you determined during risk treatment that Annex A does not cover] |  |  | M4 - Control Build-out | [5 empty] | Not Started |  | 0 - None
CC-09 | Custom | [Additional control not in Annex A] | [5 empty] | [Describe the control you determined during risk treatment that Annex A does not cover] |  |  | M4 - Control Build-out | [5 empty] | Not Started |  | 0 - None
CC-10 | Custom | [Additional control not in Annex A] | [5 empty] | [Describe the control you determined during risk treatment that Annex A does not cover] |  |  | M4 - Control Build-out | [5 empty] | Not Started |  | 0 - None
Column O is the traceability ISO/IEC 27003 asks for at 6.1.3 b): you should be able to show the relationship from each necessary control back to the risk assessment result that made it necessary. Auditors increasingly ask for it, and it is the fastest way to prove the SoA was not written independently of the risk work.
Column P offers the three exclusion reasons ISO/IEC 27003 sets out at 6.1.3 d): the control is not needed for the chosen treatment option; the control falls outside the ISMS scope; or a custom control makes it redundant. Anything that does not fit one of those three is probably not a justification, it is an excuse.
Rows CC-01 onwards are for controls you determined during risk treatment that Annex A does not cover. ISO/IEC 27003 is explicit that Annex A is not exhaustive and that additional controls belong in the SoA. Delete the unused rows.
Columns D to H carry this kit's assignment of the five ISO/IEC 27002:2022 control attributes - following ISO's scheme, not a reproduction of its attribute tables - so the control set can be filtered through more than one lens: by control type to check the preventive/detective balance, by cybersecurity concept for a CISO or NIST CSF view, by operational capability to hand work to the right team, and by security domain for board reporting. Filtering by operational capability at the start of control build-out turns a list of 93 into eight or nine work packages.

## 04 Mandatory Documents
MANDATORY DOCUMENTS AND RECORDS
What a certification auditor will ask for by name. Track document ID, version, owner and approval.
# | Document or record | Driven by | Type | Why the auditor asks for it | Exists? | Document ID | Version | Owner | Approved by | Approval date | Location | Notes
1 | ISMS Scope | 4.3 | Document | Defines what is being certified. Stage 1 fails without it. | No
2 | Information Security Policy | 5.2 | Document | Top-level commitment signed by management. | No
3 | Information Security Risk Assessment Process | 6.1.2 | Document | Must show criteria, scales and method before results are credible. | No
4 | Information Security Risk Treatment Process | 6.1.3 | Document | How treatment options and controls are chosen. | No
5 | Statement of Applicability (SoA) | 6.1.3 d | Document | The single most scrutinised ISMS document. Must cover all 93 Annex A controls. | No
6 | Risk Treatment Plan | 6.1.3 e, 8.3 | Document | Actions, owners, dates; approved by risk owners. | No
7 | Information Security Objectives | 6.2 | Document | Measurable objectives with plans to achieve them. | No
8 | Evidence of Competence | 7.2 d | Record | Certificates, training records, CVs. | No
9 | Documented information determined as necessary | 7.5.1 b | Document | Your own procedures - the document register proves you control them. | No
10 | Operational planning and control records | 8.1 | Record | Proof processes ran as planned. | No
11 | Results of information security risk assessments | 8.2 | Record | Dated risk assessment outputs. | No
12 | Results of information security risk treatment | 8.3 | Record | Evidence treatment actions were implemented. | No
13 | Monitoring and measurement results | 9.1 | Record | Metrics reports and analysis. | No
14 | Internal audit programme and results | 9.2.2 | Record | Programme, plans, reports, findings. | No
15 | Management review results | 9.3.3 | Record | Minutes with decisions and actions. | No
16 | Nonconformities and corrective actions | 10.2 | Record | Nature of NC, action taken, results. | No
17 | Asset inventory / inventory of information and associated assets | A.5.9 | Record | Underpins scope, classification and risk. | No
18 | Access control rules | A.5.15 | Document | Referenced by most technical controls. | No
19 | Incident management procedure | A.5.24 | Document | Must exist before an incident, not after. | No
20 | Legal, statutory, regulatory and contractual requirements register | A.5.31 | Record | Shows you know your obligations. | No
21 | Business continuity / ICT continuity plans | A.5.29, A.5.30 | Document | With test evidence. | No
22 | Documented operating procedures | A.5.37 | Document | Runbooks for the processes you rely on. | No
23 | Terms and conditions of employment (security clauses) | A.6.2 | Record | Sampled at audit. | No
24 | Awareness, education and training records | A.6.3 | Record | Completion evidence for all staff. | No
25 | Confidentiality / non-disclosure agreements | A.6.6 | Record | Signed, current and registered. | No
26 | Secure development policy and rules | A.8.25 | Document | Only if you develop software - state so in the SoA if not. | No
27 | Change management records | A.8.32 | Record | Sampled heavily at Stage 2. | No

## 05 Document Register
ISMS DOCUMENT REGISTER (Clauses 7.5.1 to 7.5.3)
Every ISMS document and record, internal and external. Pre-populated with a typical set - delete what you do not need.
Doc ID | Title | Type | Driven by (clause / control) | Origin | Supplied in this kit? | Owner | Approver | Version | Approval date | Review frequency | Next review | Classification | Location | Who it is distributed to | Retention | Disposition after retention | Status
POL-01 | Information Security Policy | Policy | 5.2, A.5.1 | Internal | Doc 03 |  |  |  |  | Annual | [6 empty] | Not Started
POL-02 | Acceptable Use Policy | Policy | A.5.10, A.7.7, A.8.1 | Internal | Doc 05, policy 1 |  |  |  |  | Annual | [6 empty] | Not Started
POL-03 | Access Control Policy | Policy | A.5.15-A.5.18, A.8.2-A.8.5 | Internal | Doc 05, policy 2 |  |  |  |  | Annual | [6 empty] | Not Started
POL-04 | Information Classification and Handling Policy | Policy | A.5.12-A.5.14, A.5.33 | Internal | Doc 05, policy 3 |  |  |  |  | Annual | [6 empty] | Not Started
POL-05 | Cryptographic Controls Policy | Policy | A.8.24, A.5.17 | Internal | Doc 05, policy 4 |  |  |  |  | Annual | [6 empty] | Not Started
POL-06 | Supplier and Third Party Security Policy | Policy | A.5.19-A.5.23 | Internal | Doc 05, policy 5 |  |  |  |  | Annual | [6 empty] | Not Started
POL-07 | Incident Management Policy | Policy | A.5.24-A.5.28, A.6.8 | Internal | Doc 05, policy 6 |  |  |  |  | Annual | [6 empty] | Not Started
POL-08 | Business Continuity Policy | Policy | A.5.29, A.5.30 | Internal | Doc 05, policy 7 |  |  |  |  | Annual | [6 empty] | Not Started
POL-09 | Human Resources Security Policy | Policy | A.6.1-A.6.7 | Internal | Doc 05, policy 8 |  |  |  |  | Annual | [6 empty] | Not Started
POL-10 | Physical and Environmental Security Policy | Policy | A.7.1-A.7.14 | Internal | Doc 05, policy 9 |  |  |  |  | Annual | [6 empty] | Not Started
POL-11 | Secure Development Policy | Policy | A.8.25-A.8.31, A.8.33 | Internal | Doc 05, policy 10 |  |  |  |  | Annual | [6 empty] | Not Started
POL-12 | Backup Policy | Policy | A.8.13 | Internal | Doc 05, policy 11 |  |  |  |  | Annual | [6 empty] | Not Started
POL-13 | Logging and Monitoring Policy | Policy | A.8.15-A.8.17 | Internal | Doc 05, policy 12 |  |  |  |  | Annual | [6 empty] | Not Started
POL-14 | Asset Management Policy | Policy | A.5.9-A.5.11, A.7.9, A.7.14, A.8.1 | Internal | Doc 05, policy 13 |  |  |  |  | Annual | [6 empty] | Not Started
POL-15 | Information Transfer Policy | Policy | A.5.14, A.8.20, A.8.21 | Internal | Doc 05, policy 14 |  |  |  |  | Annual | [6 empty] | Not Started
POL-16 | Secure Configuration and User Endpoint Devices Policy | Policy | A.8.1, A.8.9, A.8.19 | Internal | Doc 05, policy 15 |  |  |  |  | Annual | [6 empty] | Not Started
POL-17 | Networking Security Policy | Policy | A.8.20-A.8.23 | Internal | Doc 05, policy 16 |  |  |  |  | Annual | [6 empty] | Not Started
POL-18 | Technical Vulnerability Management Policy | Policy | A.8.8, A.8.29, A.5.7 | Internal | Doc 05, policy 17 |  |  |  |  | Annual | [6 empty] | Not Started
ISMS-01 | ISMS Scope Document | Scope | 4.3 | Internal | Doc 02 |  |  |  |  | Annual | [6 empty] | Not Started
ISMS-02 | ISMS Context Analysis | Analysis | 4.1 | Internal | Doc 02, section 3 |  |  |  |  | Annual | [6 empty] | Not Started
ISMS-03 | ISMS Process Model / Framework | Framework | 4.4 | Internal | Doc 02, section 7 |  |  |  |  | Annual | [6 empty] | Not Started
ISMS-04 | Interested Parties Register | Register | 4.2 | Internal | Tab 06 |  |  |  |  | Annual | [6 empty] | Not Started
ISMS-05 | Legal, Regulatory and Contractual Requirements Register | Register | A.5.31, A.5.32, A.5.34 | Internal | Tab 21 |  |  |  |  | Annual | [6 empty] | Not Started
ISMS-06 | ISMS Risks and Opportunities Register | Register | 6.1.1 | Internal | Tab 08 |  |  |  |  | Annual | [6 empty] | Not Started
ISMS-07 | Risk Management Methodology | Procedure | 6.1.2, 6.1.3 | Internal | Doc 04 |  |  |  |  | Annual | [6 empty] | Not Started
ISMS-08 | Information Security Risk Register | Register | 6.1.2, 8.2 | Internal | Tab 09 |  |  |  |  | Annual | [6 empty] | Not Started
ISMS-09 | Statement of Applicability | Register | 6.1.3 d | Internal | Tab 03 |  |  |  |  | Annual | [6 empty] | Not Started
ISMS-10 | Risk Treatment Plan | Plan | 6.1.3 e, 8.3 | Internal | Tab 10 |  |  |  |  | Annual | [6 empty] | Not Started
ISMS-11 | Information Security Objectives and Measurement Plan | Plan | 6.2, 9.1 | Internal | Tabs 17 and 18; Doc 10 |  |  |  |  | Annual | [6 empty] | Not Started
ISMS-12 | ISMS Communication Plan | Plan | 7.4 | Internal | Tab 13 |  |  |  |  | Annual | [6 empty] | Not Started
ISMS-13 | Competence Matrix and Training Plan | Register | 7.2 | Internal | Tab 12 |  |  |  |  | Annual | [6 empty] | Not Started
ISMS-14 | Document Control Procedure | Procedure | 7.5.2, 7.5.3 | Internal | Doc 11 |  |  |  |  | Annual | [6 empty] | Not Started
ISMS-15 | Records Retention Schedule | Schedule | 7.5.3, A.5.33 | Internal | Tab 23 |  |  |  |  | Annual | [6 empty] | Not Started
ISMS-16 | Asset Inventory | Register | A.5.9 | Internal | Tab 07 |  |  |  |  | Annual | [6 empty] | Not Started
ISMS-17 | Supplier Register | Register | A.5.19-A.5.22 | Internal | Tab 22 |  |  |  |  | Annual | [6 empty] | Not Started
ISMS-18 | Internal Audit Programme | Plan | 9.2.2 | Internal | Doc 07, Part 1 |  |  |  |  | Annual | [6 empty] | Not Started
ISMS-19 | Management Review Minutes | Record | 9.3.3 | Internal | Doc 08 |  |  |  |  | Annual | [6 empty] | Not Started
ISMS-20 | Nonconformity and Corrective Action Log | Register | 10.2 | Internal | Tab 16; Doc 09 |  |  |  |  | Annual | [6 empty] | Not Started
ISMS-21 | Continual Improvement Log | Register | 10.1 | Internal | Tab 25 |  |  |  |  | Annual | [6 empty] | Not Started
ISMS-22 | Exceptions Register | Register | 5.1, A.5.36 | Internal | Tab 20 |  |  |  |  | Annual | [6 empty] | Not Started
ISMS-23 | Contract Security Schedule (for customer and supplier contracts) | Contract | A.5.20, 4.2 | Internal | Doc 14 |  |  |  |  | Annual | [6 empty] | Not Started
ISMS-24 | Cloud Shared Responsibility Matrix | Register | A.5.23 | Internal | Tab 24 |  |  |  |  | Annual | [6 empty] | Not Started
ISMS-25 | ISMS Change Log | Register | 6.3 | Internal | Tab 19 |  |  |  |  | Annual | [6 empty] | Not Started
PRO-01 | Incident Response Plan and Runbooks | Procedure | A.5.24-A.5.26 | Internal | Doc 12 |  |  |  |  | Annual | [6 empty] | Not Started
PRO-02 | Business Continuity and ICT Recovery Plans | Plan | A.5.29, A.5.30 | Internal | Doc 13 |  |  |  |  | Annual | [6 empty] | Not Started
PRO-03 | Documented Operating Procedures (runbook library) | Procedure | A.5.37 | Internal | Doc 15 (template); content is yours to write |  |  |  |  | Annual | [6 empty] | Not Started
EXT-01 | ISO/IEC 27001:2022 and Amd 1:2024 | Standard | Normative reference | External | You must license |  |  |  |  | Annual | [6 empty] | Not Started
EXT-02 | ISO/IEC 27002:2022 | Standard | Control guidance | External | You must license |  |  |  |  | Annual | [6 empty] | Not Started
EXT-03 | ISO/IEC 27005:2022 | Standard | Risk guidance | External | You must license |  |  |  |  | Annual | [6 empty] | Not Started
EXT-04 | [Applicable data protection law, e.g. UK GDPR / EU GDPR] | Legal | A.5.31, A.5.34 | External | You must obtain |  |  |  |  | Annual | [6 empty] | Not Started
EXT-05 | [Sector regulation, e.g. DORA / NIS2 / PCI DSS] | Regulatory | A.5.31 | External | You must obtain |  |  |  |  | Annual | [6 empty] | Not Started
Column F says what the kit supplies for each entry and what you have to create. Everything marked with a Doc or Tab number already exists; anything else is yours to build. Clause 7.5.3 also requires documents of EXTERNAL origin that you determine are necessary - standards, laws, regulations, contracts, supplier documentation - to be identified and controlled. Those are the EXT- rows. Most registers forget them; auditors do not.

## 06 Interested Parties
INTERESTED PARTIES AND THEIR REQUIREMENTS (Clause 4.2)
List who cares about your information security and exactly what each one requires.
# | Interested party | Category | Their requirement or expectation | Source (contract, law, standard, policy) | Addressed by the ISMS? | How it is addressed | Owner | Review date | Notes
1 | Enterprise customers | Customer | ISO 27001 certification and completion of security questionnaires within 10 working days | Master services agreement, clause 12 | Yes | ISMS certified to ISO 27001:2022; standard security questionnaire response pack maintained | Head of Sales |  | EXAMPLE ROW - overwrite
2 | Data protection authority | Regulator | Personal data breach notification within 72 hours; demonstrable accountability | GDPR Articles 5(2), 33 | Yes | Incident Response Plan with 72-hour notification trigger; RoPA maintained | DPO |  | EXAMPLE ROW - overwrite
3 | Employees | Internal | Clear guidance on acceptable use and protection of their own personal data | Employment contract; GDPR | Yes | Acceptable Use Policy; employee privacy notice; annual awareness training | HR Director |  | EXAMPLE ROW - overwrite
ISO/IEC 27001:2022/Amd 1:2024 added a note to Clause 4.2 that relevant interested parties can have requirements related to climate change. Review this register with that specifically in mind - customer ESG questionnaires, investor or parent company reporting, insurer expectations, disclosure regimes - and record the outcome even where the answer is that none do. An auditor will ask whether you looked.

## 07 Asset Inventory
INVENTORY OF INFORMATION AND ASSOCIATED ASSETS (A.5.9)
The foundation of scope, classification and risk assessment. Keep it current.
Asset ID | Asset name | Asset type | Business owner (department) | Asset owner (person/role) | Classification | Confidentiality need | Integrity need | Availability need | Location / hosting | Supplier (if third party) | Contains personal data? | Notes
AST-001 | Customer CRM (SaaS) | Application / Cloud service | Sales | IT Lead | Confidential | High | High | Medium | EU (Ireland) | Salesforce | Yes | EXAMPLE ROW - replace with your own asset

## 08 Risks and Opportunities
ISMS RISKS AND OPPORTUNITIES (Clause 6.1.1)
NOT the information security risk register. These are risks and opportunities to the management system itself.
Clause 6.1.1 and Clause 6.1.2 are different requirements and auditors check for both. 6.1.2 asks what could happen to your information. 6.1.1 asks what could stop the ISMS from achieving its intended outcomes, what could produce undesired effects, and where the ISMS could be improved - derived from the Clause 4.1 issues and the Clause 4.2 requirements. A kit that only has an information security risk register is missing half of Clause 6.1.
ID | Type | Source | Description | Effect on the ISMS achieving its intended outcomes | Significance | Action planned | Integrated into which ISMS process | Owner | Target date | How effectiveness will be evaluated | Status
RO-001 | Risk | 4.1 Internal issue | The ISMS depends on a single part-time owner with no deputy | If that person leaves, the ISMS stops operating and certification lapses at the next surveillance audit |  | Appoint and train a deputy; document all ISMS processes so they are transferable | 1.5 ISMS resource management | [Top management] |  |  | Open
RO-002 | Risk | 4.2 Interested party requirement | Customers are asking for evidence faster than the evidence cycle produces it | Sales delays and pressure to fabricate or backdate records, undermining ISMS integrity |  | Build a standing customer assurance pack refreshed quarterly from the Evidence Log | 1.2 ISMS communication | [Head of Sales] |  |  | Open
RO-003 | Risk | 4.1 External issue | Regulatory change in scope jurisdictions could add obligations mid-implementation | Scope and SoA rework late in the programme |  | Legal register reviewed quarterly; horizon-scanning item added to committee agenda | 1.1 Requirements management | [Legal / Compliance] |  |  | Open
RO-004 | Opportunity | 4.1 Internal issue | Existing engineering change controls are already strong and evidenced in the pipeline | Several Annex A controls can be evidenced automatically rather than manually |  | Map pipeline artefacts to A.8.28-A.8.32 evidence requirements and use them directly | 2.9 Secure development and release | [Head of Engineering] |  |  | Open
RO-005 | Opportunity | 4.2 Interested party requirement | Certification unlocks a customer segment currently closed to the business | ISMS delivers commercial return, strengthening ongoing leadership commitment |  | Track pipeline attributable to certification and report it at management review | 1.9 ISMS monitoring and measurement | [Top management] |  |  | Open
Rows above in grey italic are worked examples showing the expected level of detail. Overwrite them.

## 09 Risk Register
INFORMATION SECURITY RISK REGISTER (Clauses 6.1.2 and 8.2)
Scales are 1-5. Inherent and residual scores are calculated - do not overwrite columns J, K, R or S.
Risk ID | Asset / process at risk | Risk owner | CIA affected | Risk scenario | Threat | Vulnerability / cause | Impact (1-5) | Likelihood (1-5) | Inherent score | Inherent rating | Treatment option | Controls applied (Annex A refs) | Treatment actions | Action owner | Due date | Residual impact (1-5) | Residual likelihood (1-5) | Residual score | Residual rating | Status | Notes
R-001 | Customer data in SaaS CRM | IT Lead | Confidentiality | Attacker obtains valid credentials through phishing and exports the customer database | Phishing / credential theft | No MFA enforced on CRM; staff not phishing-trained | 4 | 4 | 16 | Critical | Modify | A.5.17, A.6.3, A.8.5, A.8.16 | Enforce MFA on all CRM accounts; deliver phishing training and quarterly simulations; enable export alerting | IT Lead | 2026-10-31 | 4 | 2 | 8 | Medium | Open | EXAMPLE ROW - replace with your own risk
SCALES
Impact / Likelihood |  | 1 Very low ¦ 2 Low ¦ 3 Medium ¦ 4 High ¦ 5 Very high
Risk score |  | Impact x Likelihood (1-25)
Rating bands |  | 1-4 Low ¦ 5-9 Medium ¦ 10-14 High ¦ 15-25 Critical
Acceptance threshold |  | [SET YOUR THRESHOLD - e.g. risks scoring 9 or below may be accepted by the risk owner; 10 and above require treatment and top management acceptance]

## 10 Risk Treatment Plan
RISK TREATMENT PLAN (Clauses 6.1.3 e and 8.3)
One row per treatment action. Must be approved by risk owners before Stage 1.
Action ID | Related risk ID | Annex A control(s) | Treatment action | Treatment option | Action owner | Resources required | Start date | Target date | Status | Completion date | Evidence of completion | Control effectiveness assessed | Expected residual risk level | Residual risk accepted by | Acceptance date
RTP-001 | R-001 | A.8.5, A.5.17 | Enforce MFA for all CRM users, including administrators and integrations | Modify (reduce) | IT Lead | IdP licence uplift; 2 days engineering |  |  | Not Started |  | IdP policy screenshot + MFA coverage report
Columns M to P follow the approach ISO/IEC 27003 suggests at 6.1.3 f): record the effectiveness of the control, the residual risk it leaves, and the risk owner's acceptance of that residual risk, against the plan itself rather than in a separate document.

## 11 RACI
ISMS RACI CHART
Suggested allocation. Replace the role names with your own actual roles - one Accountable per row only.
Process / activity | ISO 27001:2022 reference | Accountable (A) | Responsible (R) | Consulted (C) | Informed (I) | Named individual | Confirmed?
0.1 ISMS design and planning (project) | 6.2, 6.3, 8.1, A.5.8 | Top Management | ISMS Manager | External adviser; IT Lead | All Staff |  | No
1.1 Requirements management (legal, contractual) | 4.2, A.5.5, A.5.31, A.5.32, A.5.34 | ISMS Manager | Legal / Compliance | DPO; Sales | Top Management |  | No
1.2 ISMS communication | 4.2, 7.4, A.5.5, A.5.6 | ISMS Manager | ISMS Manager | Comms / HR | All Staff |  | No
1.3 ISMS document management | 5.2, 7.5, A.5.1, A.5.37 | ISMS Manager | ISMS Coordinator | Document owners | All Staff |  | No
1.4 Risk management (assessment, treatment, SoA) | 6.1, 8.2, 8.3, A.5.7 | Top Management | ISMS Manager | Risk owners; IT Lead; External adviser | Security Committee |  | No
1.5 ISMS resource management | 5.1, 7.1 | Top Management | ISMS Manager | Finance; HR | Security Committee |  | No
1.6 Awareness, training and education | 7.2, 7.3, A.6.3 | ISMS Manager | HR | ISMS Manager; Line managers | All Staff |  | No
1.7 Internal audit | 9.2, A.5.35, A.5.36 | Top Management | Internal Auditor | ISMS Manager; Process owners | Security Committee |  | No
1.8 Preparation for external audits | A.5.35, A.5.36, A.8.34 | ISMS Manager | ISMS Coordinator | All process owners | Top Management |  | No
1.9 ISMS monitoring and measurement | 6.2, 9.1 | ISMS Manager | ISMS Coordinator | Control owners | Security Committee |  | No
1.10 Management review | 9.3 | Top Management | ISMS Manager | Security Committee | All process owners |  | No
1.11 Nonconformity and corrective action | 10.2 | ISMS Manager | Process owner | Internal Auditor | Top Management |  | No
1.12 Continual improvement / committee meetings | 5.1, 5.3, 6.3, 10.1, A.5.2, A.5.4 | Top Management | ISMS Manager | Security Committee | All Staff |  | No
2.1 Asset inventory | 4.3, A.5.9 | IT Lead | Asset owners | ISMS Manager | Security Committee |  | No
2.2 Access management and reviews | A.5.15-5.18, A.8.1-8.5 | IT Lead | IT Operations | System owners; HR | ISMS Manager |  | No
2.3 Incident management and notification | A.5.24-5.28, A.6.8 | ISMS Manager | Incident Response Lead | Legal; DPO; Comms; IT | Top Management |  | No
2.4 Configuration and change management | A.8.9, A.8.19, A.8.32 | IT Lead | IT Operations | ISMS Manager; Developers | Service owners |  | No
2.5 Vulnerability and patch management | A.8.8 | IT Lead | IT Operations | ISMS Manager; Developers | Security Committee |  | No
2.6 Capacity management | A.8.6 | IT Lead | IT Operations | Service owners | ISMS Manager |  | No
2.7 Backup and restore testing | A.8.13 | IT Lead | IT Operations | Data owners | ISMS Manager |  | No
2.8 Business continuity and DR testing | A.5.29, A.5.30, A.8.14 | Top Management | BC Coordinator | IT Lead; Process owners | All Staff |  | No
2.9 Secure development and release | A.8.25-8.31 | Head of Engineering | Development teams | ISMS Manager; QA | Product |  | No
2.10 Logging and monitoring | A.8.15, A.8.16, A.8.21, A.8.23 | IT Lead | Security Operations | ISMS Manager | Security Committee |  | No
2.11 Information transfer | A.5.14 | ISMS Manager | IT Operations | Legal; Data owners | All Staff |  | No
2.12 Security tooling configuration | A.8.7, A.8.12, A.8.20-8.24 | IT Lead | Security Operations | ISMS Manager | Service owners |  | No
3.1 Classification, labelling and records | 7.5, A.5.12, A.5.13, A.5.33, A.5.37 | ISMS Manager | Information owners | Legal; DPO | All Staff |  | No
3.2 Physical security | A.7.1-7.14, A.5.10, A.5.11 | Facilities Manager | Facilities / Office Manager | ISMS Manager; IT | All Staff |  | No
3.3 Human resources security | A.6.1-6.8 | HR Director | HR | ISMS Manager; Legal; Line managers | All Staff |  | No
3.4 Supplier onboarding and due diligence | A.5.19-5.21, A.5.23 | Procurement Lead | Procurement | ISMS Manager; Legal; IT | Budget holders |  | No
3.5 Supplier monitoring and review | 8.1, A.5.22, A.5.23 | Procurement Lead | Contract owners | ISMS Manager | Security Committee |  | No
3.6 Privacy and data protection | A.5.34 | DPO | DPO | Legal; ISMS Manager | All Staff |  | No
A - Accountable: one role only. Has the final yes/no and owns the outcome.
R - Responsible: does the work. Can be several roles.
C - Consulted: two-way input before the work is done.
I - Informed: one-way notification after the fact.

## 12 Competence Matrix
COMPETENCE MATRIX AND TRAINING PLAN (Clause 7.2)
Clause 7.2 d requires documented evidence of competence. This is where you track it and the gaps.
Role | Person(s) | ISMS responsibilities | Competence required | Basis (education / training / experience) | Evidence held | Gap identified? | Action to close the gap | Action owner | Target date | Was the action effective? (how verified) | Status | Evidence location
Top management / Sponsor |  | Approves scope, policy and risk acceptance; chairs management review | Understanding of ISO 27001 leadership requirements; ability to interpret risk in business terms | [7 empty] | Not Started
ISMS Manager |  | Runs the ISMS; owns risk register, SoA and documentation; reports performance | Working knowledge of ISO/IEC 27001:2022 and 27002:2022; risk assessment practice; audit awareness. Typically a lead implementer qualification | [7 empty] | Not Started
Internal Auditor |  | Audits the ISMS independently against the standard and internal requirements | Auditing technique to ISO 19011; ISO 27001 knowledge; demonstrable independence from what is audited | [7 empty] | Not Started
Risk owners |  | Own individual risks; provide impact and likelihood input; accept residual risk | Understanding of the risk methodology and scales; authority to make decisions in their area | [7 empty] | Not Started
Control owners |  | Operate assigned controls and produce evidence | Operational competence in the control area; understanding of what evidence is required and why | [7 empty] | Not Started
IT / Infrastructure Lead |  | Implements and operates technical controls | Platform-specific security competence; hardening, logging, access management, backup and recovery | [7 empty] | Not Started
Security Operations |  | Monitors, triages alerts, responds to incidents | Detection and triage skills; incident handling; forensic readiness awareness | [7 empty] | Not Started
Incident Response Lead |  | Manages incident handling and post-incident review | Incident command; escalation judgement; regulatory notification awareness | [7 empty] | Not Started
Developers / Engineering |  | Build software securely; operate pipeline controls | Secure coding for the languages in use; awareness of common vulnerability classes; use of SAST/SCA tooling | [7 empty] | Not Started
HR |  | Screening, contracts, onboarding, offboarding, awareness, disciplinary process | Employment law; the security clauses in contracts; the joiner/mover/leaver process | [7 empty] | Not Started
Legal / DPO |  | Contractual and regulatory obligations; breach notification | Data protection law; contract review; notification timelines and thresholds | [7 empty] | Not Started
Procurement / Contract owners |  | Supplier due diligence, contracts and reviews | Supplier risk tiering; ability to read assurance reports such as SOC 2 and ISO certificates | [7 empty] | Not Started
Facilities |  | Physical and environmental controls | Physical security practice; contractor and visitor management; environmental systems | [7 empty] | Not Started
All personnel |  | Comply with policies; report events | Awareness of the policy set, their own responsibilities, how to report, and the consequences of not conforming | [7 empty] | Not Started
Column K exists because ISO/IEC 27001 7.2 c) requires you to evaluate the effectiveness of the actions you took to acquire competence - not merely that training was delivered. A post-training assessment, an observed task, or a review some months after a hire all count.

## 13 Communication Plan
ISMS COMMUNICATION PLAN (Clause 7.4)
Clause 7.4 asks four questions: on what, when, with whom, and how. This answers all four, plus who does it.
# | What is communicated | Why | When / trigger / frequency | With whom (audience) | Internal or external | How (channel) | Who communicates | Who approves | How receipt and understanding are confirmed | Record kept | In place?
1 | Information Security Policy and topic policies | So people know the rules that apply to them | On approval, on change, and annually | All personnel and contractors | Internal | Intranet publication plus email; acknowledgement captured | [ISMS Manager] |  |  | Acknowledgement report | No
2 | Security awareness training | Clause 7.3 awareness obligations | At induction and at least annually | All personnel and contractors | Internal | LMS module; live session for higher-risk roles | [HR / ISMS Manager] |  |  | Completion records | No
3 | ISMS performance and metrics | So management can steer and Clause 9.1 is evidenced | [Monthly] to committee, [quarterly] to top management | Information Security Committee; top management | Internal | Metrics pack and dashboard | [ISMS Manager] |  |  | Committee minutes | No
4 | Risk status and risks accepted above threshold | So risk acceptance is visible and owned | Each committee meeting and at every management review | Committee; top management; risk owners | Internal | Risk report from the register | [ISMS Manager] |  |  | Minutes and risk register | No
5 | Internal and external audit results | Clause 9.2.2 d requires results reported to relevant management | Within [10 working days] of the audit | Auditees; ISMS Manager; top management | Internal | Audit report with distribution list | [Internal Auditor] |  |  | Audit report and distribution record | No
6 | Management review outcomes | So decisions reach the people who must act on them | Within [10 working days] of the review | Committee; process owners | Internal | Minutes and action log | [ISMS Manager] |  |  | Minutes | No
7 | Security event reporting | So events surface quickly - Clause A.6.8 | Immediately on observing or suspecting an event | [Security inbox / service desk / report button] | Internal | [CHANNEL] | Any person |  |  | Event/incident register | No
8 | Incident notification to authorities | Legal obligation, e.g. 72-hour personal data breach notification | On assessment that a notifiable breach has occurred | [Data protection authority; sector regulator; CERT] | External | [Regulator portal / formal written notice] | [DPO, approved by top management] |  |  | Copy of notification and decision record | No
9 | Incident notification to customers | Contractual obligation | Per contract, typically within [24-72 hours] | Affected customers | External | [Named contact route in contract] | [Contract owner with Legal] |  |  | Copy of notification | No
10 | Crisis communications | So a disruption is not made worse by inconsistent messaging | On activation of the crisis team | Staff, customers, regulators, press as applicable | Both | Pre-approved holding statements; single spokesperson | [Comms lead / CEO] |  |  | Comms log | No
11 | Security requirements to suppliers | So obligations are known before data is shared | At onboarding and on contract change | Suppliers and subcontractors | External | Security schedule in contract; supplier questionnaire | [Procurement / Contract owner] |  |  | Executed contract | No
12 | Certification status and assurance evidence | So customers can satisfy their own due diligence | On request and on certificate issue or renewal | Customers and prospects | External | Assurance pack; certificate; scope statement | [Head of Sales with ISMS Manager] |  |  | Assurance pack version log | No
13 | Changes to the ISMS | Clause 6.3 requires changes to be made in a planned way | Before a significant change takes effect | Affected process owners; committee | Internal | Change note to committee | [ISMS Manager] |  |  | ISMS change log | No
14 | Scope change notification | Certification bodies require notification of scope change | As soon as a scope change is decided | Certification body | External | Formal written notice | [ISMS Manager] |  |  | Correspondence file | No
Rows 5 onwards are a suggested starting set based on what certification auditors typically probe. Tailor the roles and timings, delete what does not apply, and add anything sector-specific.

## 14 Implementation Plan
PHASED IMPLEMENTATION PLAN
Indicative for a 30-250 person organisation with a moderate scope. Adjust to your own scope and resourcing.
Milestone | Indicative timing | What happens | Exit criteria | Items in this workbook | Planned start | Planned finish | Actual finish | Status | Notes
M1 - Mandate & Scope | Weeks 1-4 | Get leadership commitment, define scope and context, appoint roles, stand up governance. | Signed mandate, ISMS Scope, Context Analysis, Interested Parties Register, RACI, kickoff held | 15 |  |  |  | Not Started
M2 - Risk & Applicability | Weeks 3-10 | Build the asset inventory, agree the risk methodology, run the first risk assessment, decide controls, produce the SoA and Risk Treatment Plan. | Asset Inventory, Risk Methodology, Risk Register, Statement of Applicability, Risk Treatment Plan approved | 13 |  |  |  | Not Started
M3 - Core Documentation | Weeks 6-16 | Write the policy set, document control, competence and communication foundations. | Information Security Policy, topic policies, Document Control Procedure, Document Register, Competence Matrix | 8 |  |  |  | Not Started
M4 - Control Build-out | Weeks 8-30 | Implement the Annex A controls selected in the SoA - the bulk of the technical and process work. | Controls implemented and evidenced; Risk Treatment Plan actions closing; gap list shrinking | 0 |  |  |  | Not Started
M5 - Operate & Evidence | Weeks 20-38 | Run the ISMS for long enough to generate records: awareness, monitoring, incidents, supplier reviews, metrics. | 3+ months of operating records, metrics reported, incidents handled per procedure, awareness completed | 7 |  |  |  | Not Started
M6 - Audit & Certify | Weeks 34-52 | Internal audit across all clauses and applicable controls, close nonconformities, hold management review, then Stage 1 and Stage 2. | Internal audit complete, NCs closed, Management Review minuted, Stage 1 and Stage 2 passed | 11 |  |  |  | Not Started
SEQUENCING NOTES
M1 and M2 must be sequential. You cannot write a defensible Statement of Applicability before the risk assessment exists.
M4 is the longest phase and the one consistently underestimated. Size it from the gap assessment, not from the calendar.
M5 cannot be compressed. Certification bodies expect the ISMS to have demonstrably operated - three months of records is the usual minimum, and some bodies want more.
Internal audit (M6) must be complete and its findings closed or in progress before Stage 2. Book the certification body at the start of M5, not the end - lead times of 8-12 weeks are common.
Stage 1 is a documentation review, usually remote. Stage 2 is the deep implementation audit, usually on site. Allow 4-12 weeks between them to fix Stage 1 findings.

## 15 Evidence Log
EVIDENCE LOG / AUDIT PACK INDEX
One row per artefact you will show the auditor. Build this as you go, not the week before Stage 2.
Evidence ID | Evidence / artefact | Evidence type | Clause or control it supports | Where it lives | Owner | Date produced | Covers period | Collected? | Independently reviewed? | Notes
EV-001 | Quarterly user access review for the CRM, Q3 2026 | Record / report | A.5.18, A.8.3 | SharePoint > ISMS > 06 Evidence > Access Reviews | IT Lead |  | Q3 2026 | No | No | EXAMPLE ROW - overwrite

## 16 Nonconformities
NONCONFORMITY AND CORRECTIVE ACTION LOG (Clause 10.2)
Correction and corrective action are different things. Record both.
NC ID | Date raised | Source | Raised by | Clause / control | Description of nonconformity | Grading | Immediate correction taken | Root cause | Similar issues elsewhere? | Corrective action | Action owner | Due date | Status | Closed date | Effectiveness review (date + by whom) | Effective?
NC-001 |  | Internal audit | [Auditor name] | 9.1 | Monitoring and measurement results for Q2 were not analysed or reported to the security committee. | Minor | Q2 metrics compiled and presented at the July committee meeting retrospectively. | No owner assigned for the metrics reporting cycle; the task sat between IT and the ISMS Manager. | Yes - same gap in supplier review reporting | Assign metrics reporting to the ISMS Coordinator; add a standing agenda item and a calendar reminder; document the cycle in the measurement plan. | ISMS Manager |  | Open

## 17 Objectives
INFORMATION SECURITY OBJECTIVES (Clause 6.2)
Objectives at relevant functions and levels, each with the five planning elements 6.2 f) to j) requires.
Clause 6.2 is not the same requirement as Clause 9.1. Objectives live here; the measures that tell you whether you met them live on tab 18. Each objective should name the measure that evidences it.
Obj ID | Objective | Function / level | Derived from | Linked measure(s) | Example target | Your target | Baseline | What will be done | Resources required | Who is responsible | When it will be completed | How the results will be evaluated | Communicated to | Status | Last updated
OBJ-01 | Reduce the organisation's exposure to known technical vulnerabilities | IT / Engineering | Risk assessment | M-07 | 95% of critical vulnerabilities closed within 14 days |  |  | Introduce authenticated scanning across all production systems; agree SLAs by severity; embed remediation into sprint capacity | Scanner licence; 0.2 FTE engineering | [IT Lead] | [DATE] | Monthly review of M-07 against target at the security committee |  | Not Started
OBJ-02 | Ensure every person who handles company information understands their security responsibilities | Whole organisation | Interested party requirement; risk assessment | M-04, M-05 | 100% training completion; phishing click rate below 5% |  |  | Deliver induction and annual refresher training; run quarterly phishing simulation; add role-specific modules for engineering and finance | LMS; phishing platform; 4 days content design | [HR Director] | [DATE] | Quarterly review of M-04 and M-05; trend must be improving, not just compliant |  | Not Started
OBJ-03 | Be able to demonstrate that customer data can be recovered within agreed timeframes | IT / Engineering | Interested party requirement; contractual | M-09 | 100% of quarterly restore tests pass within the agreed RPO |  |  | Agree RPO and RTO per system with the business; implement immutable backup copies; schedule and run quarterly restore tests | Backup platform uplift; 1 day per quarter per system | [IT Lead] | [DATE] | Quarterly restore test results reviewed against agreed RPO; failures raised as nonconformities |  | Not Started
OBJ-04 | Detect and contain security incidents before they become reportable breaches | IT / Engineering | Risk assessment; legal and regulatory | M-10, M-11 | MTTD under 24 hours; MTTC under 8 hours for high severity |  |  | Centralise logging; define detection use cases from the risk register; establish on-call triage; run an annual tabletop exercise | SIEM; 0.5 FTE security operations | [Incident Response Lead] | [DATE] | Monthly MTTD and MTTC review; every outlier examined individually at post-incident review |  | Not Started
OBJ-05 | Ensure access to information is limited to those who need it | IT / Engineering; HR | Risk assessment | M-08 | 100% of access reviews completed on schedule; 100% of leavers revoked within 24 hours |  |  | Define role-based access; implement quarterly privileged access review; automate the HR leaver trigger to the identity provider | IdP configuration; 0.1 FTE | [IT Lead] | [DATE] | Quarterly access review completion and leaver revocation times reported to the committee |  | Not Started
OBJ-06 | Know and control the security risk carried by our suppliers | Procurement; Legal | Interested party requirement; contractual | M-12 | 100% of tier 1 suppliers reviewed within 12 months |  |  | Build and tier the supplier register; add the security schedule to the contract template; establish an annual review cycle | Legal review of template; 0.1 FTE procurement | [Procurement Lead] | [DATE] | Quarterly report of overdue tier 1 reviews to the committee |  | Not Started
OBJ-07 | Maintain a management system that improves rather than merely persists | Board / top management | ISO/IEC 27001 conformity; management review | M-01, M-02, M-13, M-14 | 100% of management reviews held; 90% of corrective actions verified effective |  |  | Diarise management reviews with a standing agenda; run the full internal audit cycle; track improvement actions to closure | Internal auditor time; management time | [ISMS Manager] | [DATE] | Annual assessment of suitability, adequacy and effectiveness at management review |  | Not Started
OBJ-08 | Keep changes to production from becoming security incidents | IT / Engineering | Risk assessment; incident history | M-15 | 95% of changes fully documented; 100% of emergency changes documented within 5 working days |  |  | Enforce approval and rollback fields in the change tool; reconcile deployments against change records monthly | Change tool configuration; 0.05 FTE | [IT Lead] | [DATE] | Monthly reconciliation of deployments against change records |  | Not Started
Columns I to M are the five things Clause 6.2 f) to j) requires you to determine for each objective: what will be done, what resources are needed, who is responsible, when it completes, and how results will be evaluated. Leaving any of the five blank is the most common Clause 6.2 finding.

## 18 Measurement Plan
INFORMATION SECURITY MEASUREMENT PLAN (Clause 9.1)
Each measure is specified using the information descriptors set out in ISO/IEC 27004:2016, Table 1.
Clause 9.1 asks for two different evaluations. PERFORMANCE measures tell you whether you are doing what you planned to do. EFFECTIVENESS measures tell you whether doing it made any difference to your objectives. A measurement plan made entirely of performance measures satisfies half the clause. Column F marks which is which - check you have both.
Measure ID | Information need | Measure | Formula / scoring | Example target | Type | Your target | Baseline | Implementation evidence | Frequency - collect | Frequency - report | Information owner | Information collector | Measurement client | Data source | Reporting format | Action if the target is not met | Relationship (ISO/IEC 27001:2022) | In use?
M-01 | Are the information security policies being reviewed at the planned intervals? | Percentage of policies reviewed within their review period | (Policies reviewed within review date / total policies in force) x 100 | 100% | Performance |  |  | Document register review dates; version history of each policy | Quarterly | Quarterly | [ISMS Manager] | [ISMS Coordinator] | [Information Security Committee] | Document register (workbook tab 05) | Bar chart, current period against previous four | Escalate overdue policies to their owners with a two-week deadline; report repeat offenders at management review | 5.2, 7.5.2, A.5.1 | Yes
M-02 | Is top management engaging with the ISMS as required? | Management review meetings held, and average attendance by top management | (Reviews held / reviews scheduled) x 100; and (top management attendees present / top management invited) x 100 | 100% held; attendance 80% or above | Performance |  |  | Management review minutes with attendance records | Per meeting | Annually | [ISMS Manager] | [ISMS Coordinator] | [Top management] | Management review minutes | Simple table with a note on any missed review | Raise as an ISMS risk under Clause 6.1.1 - leadership engagement is a Clause 5 conformity issue | 5.1, 9.3 | Yes
M-03 | Is the ISMS adequately resourced against what was planned? | Information security resource allocation against budget | Resources used / resources allocated, split by internal personnel, external personnel, tooling and services | Between 85% and 110% of allocation | Performance |  |  | Budget reports; timesheets or effort estimates; purchase records | Monthly | Quarterly | [Finance Business Partner] | [ISMS Manager] | [Top management] | Finance system; ISMS project plan | Stacked bar by category, allocated against used | Bring the shortfall to management review as a resource decision under Clause 7.1 | 5.1 c, 7.1 | Yes
M-04 | Have the people who need security training actually received it? | Percentage of personnel completing mandatory awareness training | (Personnel who completed / personnel assigned) x 100, including contractors | 100% within 30 days of assignment | Performance |  |  | LMS completion report; induction records | Monthly | Quarterly | [HR Director] | [HR] | [ISMS Manager] | Learning management system; HR joiners list | Line chart of completion rate over time, with a breakdown by department | Line manager escalation after 30 days; access review for persistent non-completers | 7.2, 7.3, A.6.3 | Yes
M-05 | Is the awareness programme actually changing behaviour, not just being completed? | Phishing simulation click rate and report rate | (Users who clicked / emails delivered) x 100; and (users who reported / emails delivered) x 100 | Click rate below 5%; report rate above 40% | Effectiveness |  |  | Phishing platform campaign reports | Quarterly | Quarterly | [ISMS Manager] | [Security Operations] | [Information Security Committee] | Phishing simulation platform | Two line charts on one axis, click rate falling against report rate rising | Targeted follow-up training for repeat clickers; review content difficulty before concluding people are at fault | 7.3, A.6.3, A.6.8 | Yes
M-06 | Is the risk treatment plan being delivered as agreed? | Percentage of risk treatment actions completed by their target date | (Actions completed on or before target date / actions due in period) x 100 | 90% or above | Performance |  |  | Risk treatment plan with completion dates and evidence references | Monthly | Monthly | [ISMS Manager] | [ISMS Coordinator] | [Top management] | Risk treatment plan (workbook tab 10) | Burn-down chart of open actions against plan | Re-plan with the risk owner and record the revised residual risk exposure in the interim | 6.1.3, 8.3 | Yes
M-07 | Are known technical vulnerabilities being closed before they can realistically be exploited? | Percentage of critical and high vulnerabilities remediated within the defined SLA | (Vulnerabilities closed within SLA / vulnerabilities raised in period) x 100, reported separately by severity | Critical 95%; High 90% | Effectiveness |  |  | Scanner ticket history showing detection and closure timestamps | Continuous | Monthly | [IT Lead] | [Security Operations] | [Information Security Committee] | Vulnerability scanner; ticketing system | Line chart by severity, plus a count of items currently past SLA | Root cause the delay: capacity, ownership or dependency. Escalate anything over 30 days past SLA | A.8.8, A.8.9 | Yes
M-08 | Do people have only the access they should have, and is it removed promptly when they leave? | Access review completion rate, and leaver access revocation time | (Reviews completed on schedule / reviews due) x 100; and mean hours between exit date and access disabled | Reviews 100%; revocation within 24 hours for 100% of leavers | Effectiveness |  |  | Access review records showing changes made; IdP deactivation logs against HR exit dates | Per review cycle; per leaver | Quarterly | [IT Lead] | [IT Operations] | [ISMS Manager] | Identity provider; HR system; access review tracker | Table of reviews by system, plus a histogram of revocation times | Any revocation over 24 hours is investigated individually and the HR-to-IT notification path reviewed | A.5.18, A.8.2, A.8.3 | Yes
M-09 | If we lost data today, could we actually get it back within the agreed recovery point? | Restore test success rate and actual recovery point achieved | (Successful restores / restores attempted) x 100; and actual RPO achieved against agreed RPO per system | 100% success; actual RPO within agreed RPO | Effectiveness |  |  | Restore test records showing data restored, time taken and verification performed | Quarterly for critical systems | Quarterly | [IT Lead] | [IT Operations] | [Top management] | Backup platform; restore test log | Table by system: agreed RPO, achieved RPO, pass or fail | A failed restore is raised as a nonconformity immediately, not carried as a metric | A.8.13, A.5.30 | Yes
M-10 | How quickly do we notice and contain security incidents? | Mean time to detect and mean time to contain | Mean of (detection time minus occurrence time); mean of (containment time minus detection time), by severity | MTTD under 24 hours; MTTC under 8 hours for high severity | Effectiveness |  |  | Incident records with a timeline showing occurrence, detection and containment | Per incident | Monthly | [Incident Response Lead] | [Security Operations] | [Information Security Committee] | Incident register; SIEM | Box plot or simple mean by severity, with each outlier named | Post-incident review examines the detection gap specifically, and feeds detection rules under A.8.16 | A.5.24, A.5.25, A.5.26, A.8.16 | Yes
M-11 | Are people reporting the things they see, or staying quiet? | Security events reported by personnel, per 100 staff | (Events reported by personnel / headcount) x 100 | Trending upward, then stable. A very low number is a warning, not a success | Effectiveness |  |  | Event register with the reporting source recorded | Monthly | Quarterly | [ISMS Manager] | [Service Desk] | [Information Security Committee] | Event and incident register; service desk | Line chart over time, annotated with awareness campaign dates | Investigate whether the channel is known and whether reporters were treated well. Low reporting usually means fear or friction, not safety | A.6.8, A.5.25 | Yes
M-12 | Are the suppliers who hold our data actually being reviewed? | Percentage of tier 1 suppliers reviewed within the last 12 months | (Tier 1 suppliers with a review completed in the last 12 months / total tier 1 suppliers) x 100 | 100% | Performance |  |  | Supplier review records with dates and assurance evidence attached | Quarterly | Quarterly | [Procurement Lead] | [Contract owners] | [ISMS Manager] | Supplier register | Table of overdue reviews by supplier and owner | Escalate to the budget holder. An unreviewed tier 1 supplier is a risk register entry, not just a missed task | A.5.19, A.5.22, A.5.23 | Yes
M-13 | When we fix a nonconformity, does it stay fixed? | Percentage of corrective actions confirmed effective at their effectiveness review | (Corrective actions verified effective / corrective actions reviewed in period) x 100 | 90% or above | Effectiveness |  |  | Nonconformity records with a dated effectiveness review by someone other than the implementer | Per corrective action | Quarterly | [ISMS Manager] | [Internal Auditor] | [Top management] | Nonconformity log (workbook tab 16) | Table of corrective actions with verdicts, and a count of recurrences | A corrective action judged ineffective is reopened with a fresh root cause analysis, not closed again | 10.2 d | Yes
M-14 | Is the audit programme covering the whole ISMS within the planned cycle? | Percentage of ISMS clauses and applicable controls audited within the programme cycle | (Clauses and applicable controls audited / total in scope) x 100, cumulative across the cycle | 100% by the end of the cycle | Performance |  |  | Audit programme with coverage mapping; individual audit reports | Per audit | Annually | [Internal Auditor] | [Internal Auditor] | [Top management] | Internal audit programme | Coverage heat map against the clause and control list | Re-plan the remaining cycle. Uncovered areas at the end of a cycle are a Clause 9.2 nonconformity | 9.2.2 | Yes
M-15 | Are changes to production going through the change process? | Percentage of production changes with recorded approval, testing and rollback plan | (Changes with complete records / total changes deployed) x 100, with emergency changes shown separately | 95% overall; 100% of emergency changes retrospectively documented within 5 working days | Performance |  |  | Change records; deployment pipeline logs reconciled against the change register | Monthly | Monthly | [IT Lead] | [IT Operations] | [ISMS Manager] | Change management system; CI/CD logs | Bar chart, planned against emergency, with the undocumented count called out | Reconcile deployments against change records and investigate any deployment with no corresponding change | A.8.32, 8.1 | Yes
ISO/IEC 27004:2016 recommends implementing performance measures first, so you can confirm the process or control is actually operating, and adding effectiveness measures once the performance measures are hitting target. Trying to measure effectiveness of something that is not yet reliably happening produces noise.
It also warns against measuring too much. Every measure costs collection and analysis effort, and a crowded report buries the two or three numbers that matter. Start with six to eight and add only when a real information need appears.
Measurement roles (27004, 6.5): measurement client, measurement planner, measurement reviewer, information owner, information collector, information analyst, information communicator. One person can hold several - but the client and the collector should not be the same person if you can avoid it.

## 19 ISMS Change Log
ISMS CHANGE LOG (Clause 6.3 - Planning of changes)
Clause 6.3 is new in the 2022 revision and ISO/IEC 27003:2017 predates it. This tab is best practice, not guidance-derived.
Clause 6.3 says changes to the ISMS shall be carried out in a planned manner. It does not say what 'planned' looks like, and no guidance standard covers it yet. What satisfies an auditor in practice is evidence that someone considered the consequences of a change to the management system BEFORE making it - not the technical change process under A.8.32, which is a different control about production systems.
Change ID | Date raised | Raised by | What is changing | Type of ISMS change | Reason for the change | Parts of the ISMS affected | Impact on scope | Impact on risk assessment or SoA | Impact on documented information | Resources required | Who must be informed | Approved by | Approval date | Planned implementation date | Status | Post-change review (date + outcome)
CHG-001 |  | [ISMS Manager] | Bring the newly acquired [OFFICE / ENTITY] inside the ISMS scope | Scope change | Acquisition completed; the entity handles customer data covered by existing contracts | Scope document; asset inventory; risk register; SoA; supplier register; awareness programme | Yes - scope statement must be reissued and the certification body notified | Yes - full risk assessment of the new entity; SoA reviewed for controls previously excluded on scope grounds | Scope, SoA, asset inventory, RACI, document register | 10 external adviser days; 0.3 FTE internally for one quarter | Top management; certification body; affected staff; key customers |  |  |  | Proposed | EXAMPLE ROW - overwrite. A post-change review three months later confirms the change landed as planned.
What counts as an ISMS change: scope, organisational structure, top management, the risk methodology or acceptance criteria, the policy set, a major new service or platform, a critical supplier, the legal landscape, or a significant change in resourcing. Routine production changes belong in the change management process under A.8.32, not here.
Certification bodies must be notified of scope changes. Column H exists so that never gets missed.

## 20 Exceptions Register
EXCEPTIONS REGISTER
Every topic-specific policy sends exceptions here. Without this register those clauses point at nothing.
An exception is a documented decision to accept non-compliance with a stated rule for a stated period. It is not a way of avoiding a control indefinitely. Two things make an exception defensible at audit: a compensating control, and an expiry date that is a real date. ISO/IEC 27002 A.5.36 expects compliance with policies to be reviewed - an exception is how a known deviation stays visible rather than becoming quiet drift.
Exception ID | Date raised | Raised by | Policy or control excepted | What is being excepted | Business reason | Systems / people affected | Risk created | Risk ID (tab 09) | Compensating control | Residual risk rating | Approved by | Approval date | Expiry date | Review outcome | Status
EXC-001 |  | [Head of Engineering] | Access Control Policy - unique named accounts (A.5.16) | A shared service account is used by the deployment pipeline because the legacy build server cannot authenticate as an individual | Replacing the build server is scheduled for Q3; blocking deployment until then would halt releases | Build server; 4 engineers who hold the credential | Actions taken by the pipeline cannot be attributed to an individual | R-014 | Credential held in the secrets vault with checkout logging; pipeline actions logged separately and reviewed weekly; credential rotated monthly | Medium | [CISO] |  |  | EXAMPLE ROW - overwrite. Expiry must be a real date, not 'ongoing'. | Open
An exception with no expiry date is not an exception, it is an undocumented policy change. An exception renewed three times without progress is a signal the rule itself is wrong - change the policy or fix the gap, but stop renewing.

## 21 Legal Register
LEGAL, REGULATORY AND CONTRACTUAL REQUIREMENTS REGISTER (A.5.31)
Identify the requirements, document them, document how you meet each one, and keep it current.
A.5.31 asks for three things and organisations usually deliver two: the requirement, the source, and - the one that gets missed - the organisation's approach to meeting it. The 'How we satisfy it' column is that third thing. A.5.32 (intellectual property) and A.5.34 (privacy and PII) are satisfied through this same register rather than through separate ones.
Ref | Type | Requirement / obligation | Source (law, regulation, contract, clause) | Jurisdiction | Applies to (scope area) | What we must do | How we satisfy it | Related controls | Owner | Evidence location | Last reviewed | Next review | Compliance status | Notes
LR-001 | Data protection law | Notify the supervisory authority of a personal data breach without undue delay and, where feasible, within 72 hours of becoming aware of it | [UK GDPR / EU GDPR] Article 33 | [UK / EU] | All personal data processing in scope | Detect, assess and notify within the deadline; document all breaches whether notified or not | Incident Response Plan with a 72-hour trigger; DPO on the escalation path; breach register maintained | A.5.24, A.5.26, A.5.34, A.6.8 | [DPO] | [LOCATION] |  |  | Compliant
LR-002 | Data protection law | Maintain a record of processing activities | [UK GDPR / EU GDPR] Article 30 | [UK / EU] | All personal data processing in scope | Keep a current RoPA covering purposes, categories, recipients, transfers and retention | RoPA maintained by the DPO and reviewed annually | A.5.34, A.5.9 | [DPO] | [LOCATION] |  |  | Compliant
LR-003 | Contractual | Notify affected customers of a security incident affecting their data within the contractual deadline | [Master services agreement, clause X] | [N/A] | Customer data in scope services | Identify affected customers and notify through the named contact route within [24-72] hours | Incident Response Plan customer notification step; contract owner on the escalation path | A.5.20, A.5.26 | [Contract owner] | [LOCATION] |  |  | Compliant
LR-004 | Contractual | Maintain ISO/IEC 27001 certification for the scope covering the contracted services | [Master services agreement, security schedule] | [N/A] | Certified scope | Hold and maintain a valid certificate; notify the customer of any scope change or suspension | Certification maintained; scope changes routed through the ISMS Change Log | 9.2, 9.3, 6.3 | [Head of Sales] | [LOCATION] |  |  | Compliant
LR-005 | Intellectual property | Use only properly licensed software and respect third-party licence terms | [Applicable copyright legislation] | [Jurisdiction] | All systems in scope | Track licences held against software deployed; observe open-source licence obligations | Software licence register; composition analysis in the build pipeline | A.5.32, A.8.8 | [IT Lead] | [LOCATION] |  |  | Compliant
LR-006 | Sector regulation | [e.g. DORA, NIS2, PCI DSS obligation - delete if none applies] | [Regulation and article] | [Jurisdiction] | [Scope area] | [What it requires] | [How you satisfy it] | [Controls] | [Owner] | [LOCATION] |  |  | Under review
LR-007 | Cryptography | Observe any restriction on the use, import or export of cryptography in the jurisdictions of operation | [Applicable export control regime] | [Jurisdictions] | All encrypted systems and products | Check restrictions before deploying cryptography in a new jurisdiction | Cryptographic Controls Policy; legal check at market entry | A.8.24, A.5.31 | [Legal] | [LOCATION] |  |  | Compliant
Review at least annually and whenever entering a new market, signing a materially different contract, or launching a service that processes a new category of data. Horizon-scanning for forthcoming regulation belongs on tab 08 as an ISMS risk, not here.

## 22 Supplier Register
SUPPLIER REGISTER (A.5.19 to A.5.23)
Tier by risk, assess before onboarding, contract properly, review while the relationship lasts, and plan the exit.
Tiering is the decision that makes the rest proportionate. Tier 1 is anything holding information classified Confidential or above, or on which a critical service depends. Do the deep due diligence there and keep it light elsewhere - trying to assess every supplier equally means none get assessed properly. The subprocessor and exit-plan columns are the two most often missing when a customer audits you.
Supplier ID | Supplier name | Service provided | Internal owner | Tier | Handles our or customer data? | Data categories | Personal data? | Data location | Subprocessors used? | Contract in place? | Security schedule / DPA in place? | Incident notification deadline | Assurance evidence held | Assurance expiry | Last review | Next review | Exit plan in place? | Criticality to service delivery | Status | Notes
SUP-001 | [Cloud infrastructure provider] | Hosting for the production platform | [IT Lead] | Tier 1 - critical | Yes | Customer data; system logs | Yes | [EU - Ireland] | Yes - notified under contract | Yes | Yes - security schedule and DPA | 24 hours | ISO 27001 certificate; SOC 2 Type II report |  |  |  | Yes | Total - no service without it | Active | EXAMPLE ROW - overwrite
A supplier holding customer data with no security schedule, no assurance evidence and no exit plan is a finding waiting to happen and a genuine business risk. Filter on Tier 1 and check those three columns first.

## 23 Retention Schedule
RECORDS RETENTION SCHEDULE (7.5.3, A.5.33, A.8.10)
How long each record type is kept, what starts the clock, and what happens when the period ends.
Clause 7.5.3 requires retention AND disposition to be addressed, and A.8.10 requires information to be deleted when no longer needed. The disposition column is the half that gets forgotten. Two columns here exist because they are where deletion actually fails: whether the deletion also has to reach backups, and which third parties hold their own copy.
Ref | Record type | Owner | Classification | Contains personal data? | Retention period | Retention trigger (starts from) | Basis for the period | Storage location | Format | Disposition at end of period | Deletion also required in backups? | Third parties holding a copy | Last reviewed | Notes
RET-01 | ISMS records - audit reports, management reviews, nonconformities | [ISMS Manager] | Internal | No | 3 years | Date of record | Certification body expects the current and two prior cycles | [LOCATION] | Electronic | Secure destruction | No | None
RET-02 | Risk assessments and treatment plans | [ISMS Manager] | Confidential | No | 3 years after superseded | Date superseded | Traceability of risk decisions across audit cycles | [LOCATION] | Electronic | Secure destruction | No | None
RET-03 | Security event and incident records | [ISMS Manager] | Confidential | Sometimes | [3 years] | Date incident closed | Investigation, trend analysis and potential legal need | [LOCATION] | Electronic | Secure destruction | Yes | [SIEM provider]
RET-04 | System and security logs | [IT Lead] | Confidential | Sometimes | [12 months] | Date generated | Investigation window; balance against data minimisation | [Log platform] | Electronic | Automatic expiry | Yes | [Log platform provider]
RET-05 | Access review records | [IT Lead] | Internal | Yes - names | 3 years | Date of review | Demonstrating the control operated across audit cycles | [LOCATION] | Electronic | Secure destruction | No | None
RET-06 | Employee records including screening and training | [HR Director] | Confidential | Yes | [Duration of employment plus 6 years] | Date employment ends | [Employment law and limitation period in the jurisdiction] | [HR system] | Electronic | Secure destruction | Yes | [HR system provider]
RET-07 | Customer personal data held in the platform | [Data owner] | Confidential | Yes | [Per contract - typically 30 days after termination] | Contract termination | Contractual commitment and data minimisation | [Platform] | Electronic | Secure deletion with confirmation to the customer | Yes | [Cloud provider]
RET-08 | Contracts and security schedules | [Legal] | Confidential | No | [6 years after expiry] | Contract expiry | [Limitation period] | [Contract repository] | Electronic | Archive then secure destruction | No | None
RET-09 | CCTV and physical access records | [Facilities Manager] | Confidential | Yes | [30 days CCTV; 12 months entry logs] | Date recorded | Investigation need balanced against privacy and proportionality | [On-site system] | Electronic | Automatic overwrite | No | [Monitoring provider]
RET-10 | Backups | [IT Lead] | Confidential | Yes | [30 days operational; 12 months archival] | Date taken | Recovery point requirements from the BIA | [Backup platform] | Electronic | Automatic expiry | n/a - this is the backup | [Backup provider] |  | Backups are the reason deletion elsewhere is rarely complete on day one. State the lag.
Retention periods should be justified, not inherited. Where the basis is a limitation period or a statutory minimum, name it in the 'Basis' column - an auditor asking why you keep something for six years wants a reason, not a habit.

## 24 Cloud Responsibility
CLOUD SHARED RESPONSIBILITY MATRIX (A.5.23)
One row per cloud service. Who is responsible for what, and what falls between the two of you.
A.5.23 asks the organisation to define which controls the provider manages and which it manages itself. The provider publishes their version of this; it is written to describe their obligations, not yours. The column that earns its place is 'Shared / needs agreement' - the items neither side clearly owns are exactly where incidents and audit findings come from. Cloud agreements are usually not negotiable, so read them and record what you are accepting rather than assuming it can be changed.
Ref | Cloud service | Provider | Service model | Internal owner | Business purpose | Data held | Personal data? | Region(s) | Provider is responsible for | We are responsible for | Shared / needs agreement | Configuration baseline reference | Assurance evidence | Approved? | Approval date | Exit plan | Last review | Notes
CLD-01 | [Production infrastructure] | [Provider] | IaaS | [IT Lead] | Hosts the production platform | Customer data; logs | Yes | [EU - Ireland] | Physical security of data centres; hypervisor and host patching; hardware lifecycle; availability of the underlying region | Guest OS patching; network and firewall rules; IAM and MFA; encryption configuration and key management; logging and monitoring; backup and restore of our data; data classification | Incident notification timing and format; vulnerability disclosure; region change notification | [Baseline ref] | ISO 27001 certificate; SOC 2 Type II | Yes |  | [Documented - data export format, timescale, deletion confirmation] |  | EXAMPLE ROW - overwrite
CLD-02 | [SaaS CRM] | [Provider] | SaaS | [Head of Sales] | Customer relationship management | Customer contact data | Yes | [EU] | Application security; platform availability; infrastructure; patching of the application | User provisioning and deprovisioning; role configuration; MFA enforcement; sharing and export settings; what data we choose to put in it; our own backup of the data | Retention configuration; subprocessor notification; audit rights | [Baseline ref] | [Certificate] | Yes |  | [Export route and deletion commitment]
CLD-03
A.5.23 also expects selection criteria, how assurance is obtained, how incidents involving the service are handled, how multiple providers are managed together, and an exit strategy. Selection criteria and incident handling live in the Supplier and Third Party Security Policy; exit and assurance are columns here.

## 25 Continual Improvement
CONTINUAL IMPROVEMENT LOG (Clause 10.1)
Improvement opportunities from every source, evaluated, decided, and tracked to an effectiveness check.
Clause 10.1 requires continual improvement of the suitability, adequacy and effectiveness of the ISMS. ISO/IEC 27003 adds that efficiency is a legitimate target too - an ISMS that achieves its outcomes at unreasonable cost has an improvement opportunity even with no nonconformity. Improvements are evaluated, planned and their effectiveness assessed as a subset of the actions under Clause 6.1.1, which is why the last column matters as much as the first.
Ref | Date raised | Raised by | Source | Opportunity | Which aspect it improves | Expected benefit | Worth pursuing? | Decision rationale | Change required to the ISMS | Owner | Target date | Status | Completion date | Effectiveness of the action | Notes
CI-001 |  | [Internal Auditor] | Internal audit | Access reviews are performed correctly but take three weeks of manual spreadsheet work each quarter | Efficiency | Frees roughly six days a year and reduces the chance of transcription error | Yes | Cost of the tooling is recovered within two review cycles | Access Control Policy updated to reference the automated review; procedure rewritten | [IT Lead] |  | Proposed |  |  | EXAMPLE ROW - overwrite. Note that ISO/IEC 27003 treats efficiency as a legitimate improvement target alongside suitability, adequacy and effectiveness.
Keep this separate from the nonconformity log on tab 19. A nonconformity is a failure to meet a requirement and must be corrected; an improvement is optional and is chosen. Mixing them makes the corrective action process look busier than it is and hides the real findings.

## 26 Lookups
LOOKUP LISTS
Reference lists used by the dropdowns.
Status | Maturity | Milestone | Classification | Treatment option | SoA inclusion justification | Annex A theme | NC grading
Not Started | 0 - None | M1 - Mandate & Scope | Public | Modify (reduce) | Risk assessment | Organizational | Major
In Progress | 1 - Initial | M2 - Risk & Applicability | Internal | Avoid | Legal or regulatory requirement | People | Minor
Implemented | 2 - Repeatable | M3 - Core Documentation | Confidential | Share (transfer) | Contractual requirement | Physical | Observation
Verified | 3 - Defined | M4 - Control Build-out | Strictly Confidential | Retain (accept) | Business requirement | Technological | Opportunity for improvement
Not Applicable | 4 - Managed | M5 - Operate & Evidence |  |  | Best practice / ISO 27002
| 5 - Optimising | M6 - Audit & Certify |  |  | Not applicable